## Sheet1
machine_index | gap_start | gap_end | gap_duration | gap_type | setup_time | idle_time | theoretical_setup_time | prev_task_id | next_task_id | setup_reason | gap_start_minutes | gap_end_minutes | gap_duration_minutes | setup_time_minutes | idle_time_minutes | theoretical_setup_time_minutes
0 | 53 | 55 | 2 | pure_setup | 2 | 0 | 4 | 32023_투명점착_1500_T0915_0_M5 | 31704_TOP COATING_1500_T01715_0_M5 | mixture_change+operation_type_change | 1590 | 1650 | 60 | 60 | 0 | 120
0 | 57 | 59 | 2 | pure_setup | 2 | 0 | 2 | 31704_TOP COATING_1500_T01715_0_M5 | 32023_TOP COATING_1500_T01713_0_M5 | mixture_change | 1710 | 1770 | 60 | 60 | 0 | 60
0 | 62 | 66 | 4 | setup_plus_idle | 2 | 2 | 2 | 32023_TOP COATING_1500_T01713_0_M5 | 32528_비산점착_1300_T01862_4_M5 | mixture_change+operation_type_change+width_long_to_short | 1860 | 1980 | 120 | 60 | 60 | 60
0 | 80 | 82 | 2 | pure_setup | 2 | 0 | 4 | 32528_비산점착_1300_T01862_4_M5 | 31772_ESR_1300_T01020_4_M5 | mixture_change+operation_type_change | 2400 | 2460 | 60 | 60 | 0 | 120
0 | 87 | 91 | 4 | setup_plus_idle | 2 | 2 | 2 | 31772_ESR_1300_T01020_4_M5 | 31772_비산점착_1300_T01226_4_M5 | mixture_change+operation_type_change | 2610 | 2730 | 120 | 60 | 60 | 60
0 | 95 | 99 | 4 | pure_setup | 4 | 0 | 4 | 31772_비산점착_1300_T01226_4_M5 | 29059_비산점착_1500_T01792_0_M6 | mixture_change+width_short_to_long | 2850 | 2970 | 120 | 120 | 0 | 120
0 | 119 | 123 | 4 | pure_setup | 4 | 0 | 4 | 29059_비산점착_1500_T01792_0_M6 | 32470_PPF점착_1500_T0915_0_M6 | mixture_change | 3570 | 3690 | 120 | 120 | 0 | 120
0 | 125 | 129 | 4 | pure_setup | 4 | 0 | 4 | 32470_PPF점착_1500_T0915_0_M6 | 32739_PPF점착_1500_T02098_0_M6 | mixture_change | 3750 | 3870 | 120 | 120 | 0 | 120
0 | 135 | 137 | 2 | pure_setup | 2 | 0 | 4 | 32739_PPF점착_1500_T02098_0_M6 | 32470_TOP COATING_1500_T01521_0_M6 | mixture_change+operation_type_change | 4050 | 4110 | 60 | 60 | 0 | 120
0 | 139 | 141 | 2 | pure_setup | 2 | 0 | 2 | 32470_TOP COATING_1500_T01521_0_M6 | 32739_TOP COATING_1500_T02244_0_M6 | mixture_change | 4170 | 4230 | 60 | 60 | 0 | 60
0 | 147 | 151 | 4 | setup_plus_idle | 2 | 2 | 2 | 32739_TOP COATING_1500_T02244_0_M6 | 25033_염료점착_1500_T02516_0_M6 | mixture_change+operation_type_change | 4410 | 4530 | 120 | 60 | 60 | 60
0 | 156 | 160 | 4 | pure_setup | 4 | 0 | 4 | 25033_염료점착_1500_T02516_0_M6 | 25278_비산점착_1500_T02560_0_M6 | mixture_change+operation_type_change | 4680 | 4800 | 120 | 120 | 0 | 120
0 | 186 | 188 | 2 | pure_setup | 2 | 0 | 4 | 25278_비산점착_1500_T02560_0_M6 | 31772_ESR_1300_T01020_4_M6 | mixture_change+operation_type_change+width_long_to_short | 5580 | 5640 | 60 | 60 | 0 | 120
0 | 311 | 313 | 2 | pure_setup | 2 | 0 | 2 | 32556_ESR_1300_T01020_4_M6 | 32556_ESR_1000_T01020_1_M6 | width_long_to_short | 9330 | 9390 | 60 | 60 | 0 | 60
0 | 331 | 335 | 4 | setup_plus_idle | 2 | 2 | 2 | 32556_ESR_1000_T01020_1_M6 | 31772_비산점착_1300_T01226_4_M6 | mixture_change+operation_type_change+width_short_to_long | 9930 | 10050 | 120 | 60 | 60 | 60
0 | 433 | 435 | 2 | pure_setup | 2 | 0 | 2 | 32556_비산점착_1300_T01226_4_M6 | 32556_비산점착_1000_T01226_1_M6 | width_long_to_short | 12990 | 13050 | 60 | 60 | 0 | 60
0 | 449 | 451 | 2 | pure_setup | 2 | 0 | 4 | 32556_비산점착_1000_T01226_1_M6 | 32174_TOP COATING_1500_T02116_0_M6 | mixture_change+operation_type_change+width_short_to_long | 13470 | 13530 | 60 | 60 | 0 | 120
0 | 452 | 456 | 4 | setup_plus_idle | 2 | 2 | 2 | 32174_TOP COATING_1500_T02116_0_M6 | 32174_PPF점착_1500_T01852_0_M6 | mixture_change+operation_type_change | 13560 | 13680 | 120 | 60 | 60 | 60
0 | 457 | 461 | 4 | pure_setup | 4 | 0 | 4 | 32174_PPF점착_1500_T01852_0_M6 | 32023_투명점착_1500_T0915_0_M6 | mixture_change | 13710 | 13830 | 120 | 120 | 0 | 120
0 | 472 | 474 | 2 | pure_setup | 2 | 0 | 4 | 32023_투명점착_1500_T0915_0_M6 | 32023_TOP COATING_1500_T01713_0_M6 | mixture_change+operation_type_change | 14160 | 14220 | 60 | 60 | 0 | 120
0 | 485 | 489 | 4 | setup_plus_idle | 2 | 2 | 2 | 32023_TOP COATING_1500_T01713_0_M6 | 32474_안료점착_1500_T01445_0_M6 | mixture_change+operation_type_change | 14550 | 14670 | 120 | 60 | 60 | 60
0 | 490 | 494 | 4 | pure_setup | 4 | 0 | 4 | 32474_안료점착_1500_T01445_0_M6 | 32474_PPF점착_1500_T01306_0_M6 | mixture_change+operation_type_change | 14700 | 14820 | 120 | 120 | 0 | 120
0 | 495 | 499 | 4 | pure_setup | 4 | 0 | 4 | 32474_PPF점착_1500_T01306_0_M6 | 32415_PPF점착_1500_T02116_0_M6 | mixture_change | 14850 | 14970 | 120 | 120 | 0 | 120
0 | 505 | 509 | 4 | pure_setup | 4 | 0 | 4 | 32415_PPF점착_1500_T02116_0_M6 | 32453_PPF점착_1500_T01543_0_M6 | mixture_change | 15150 | 15270 | 120 | 120 | 0 | 120
0 | 520 | 522 | 2 | pure_setup | 2 | 0 | 4 | 32453_PPF점착_1500_T01543_0_M6 | 32474_TOP COATING_1500_T02244_0_M6 | mixture_change+operation_type_change | 15600 | 15660 | 60 | 60 | 0 | 120
0 | 534 | 536 | 2 | pure_setup | 2 | 0 | 2 | 32453_TOP COATING_1500_T02244_0_M6 | 32415_TOP COATING_1500_T02116_0_M6 | mixture_change | 16020 | 16080 | 60 | 60 | 0 | 60
0 | 543 | 547 | 4 | setup_plus_idle | 2 | 2 | 2 | 32415_TOP COATING_1500_T02116_0_M6 | 32472_BLACK EPU코팅_1500_14774_0_M6 | mixture_change+operation_type_change | 16290 | 16410 | 120 | 60 | 60 | 60
0 | 551 | 553 | 2 | pure_setup | 2 | 0 | 4 | 32472_BLACK EPU코팅_1500_14774_0_M6 | 32472_TOP COATING_1500_T01514_0_M6 | mixture_change+operation_type_change | 16530 | 16590 | 60 | 60 | 0 | 120
0 | 556 | 560 | 4 | setup_plus_idle | 2 | 2 | 2 | 32472_TOP COATING_1500_T01514_0_M6 | 32198_PPF점착_1500_T0915_0_M6 | mixture_change+operation_type_change | 16680 | 16800 | 120 | 60 | 60 | 60
0 | 561 | 563 | 2 | pure_setup | 2 | 0 | 4 | 32198_PPF점착_1500_T0915_0_M6 | 32198_TOP COATING_1500_T01576_0_M6 | mixture_change+operation_type_change | 16830 | 16890 | 60 | 60 | 0 | 120
0 | 564 | 566 | 2 | pure_setup | 2 | 0 | 2 | 32198_TOP COATING_1500_T01576_0_M6 | 31772_ESR_1000_T01020_1_M6 | mixture_change+width_long_to_short | 16920 | 16980 | 60 | 60 | 0 | 60
0 | 574 | 578 | 4 | setup_plus_idle | 2 | 2 | 2 | 31772_ESR_1000_T01020_1_M6 | 31772_비산점착_1000_T01226_1_M6 | mixture_change+operation_type_change | 17220 | 17340 | 120 | 60 | 60 | 60
0 | 584 | 588 | 4 | pure_setup | 4 | 0 | 4 | 31772_비산점착_1000_T01226_1_M6 | 30863_비산점착_1500_W1558_0_M7 | mixture_change+width_short_to_long | 17520 | 17640 | 120 | 120 | 0 | 120
0 | 608 | 612 | 4 | pure_setup | 4 | 0 | 4 | 30863_비산접착(1차)_1500_W1558_0_M7 | 31966_PPF점착_1500_T0915_0_M7 | mixture_change | 18240 | 18360 | 120 | 120 | 0 | 120
0 | 689 | 693 | 4 | pure_setup | 4 | 0 | 4 | 32023_투명점착_1500_T0915_0_M7 | 32431_PPF점착_1500_T01514_0_M7 | mixture_change | 20670 | 20790 | 120 | 120 | 0 | 120
0 | 696 | 700 | 4 | pure_setup | 4 | 0 | 4 | 32431_PPF점착_1500_T01514_0_M7 | 31966_TOP COATING_1500_T01288_0_M7 | mixture_change+operation_type_change | 20880 | 21000 | 120 | 120 | 0 | 120
0 | 783 | 785 | 2 | pure_setup | 2 | 0 | 2 | 31966_TOP COATING_1500_T01288_0_M7 | 32023_TOP COATING_1500_T01713_0_M7 | mixture_change | 23490 | 23550 | 60 | 60 | 0 | 60
0 | 796 | 798 | 2 | pure_setup | 2 | 0 | 2 | 32023_TOP COATING_1500_T01713_0_M7 | 32431_TOP COATING_1500_T02116_0_M7 | mixture_change | 23880 | 23940 | 60 | 60 | 0 | 60
0 | 802 | 804 | 2 | pure_setup | 2 | 0 | 2 | 32431_TOP COATING_1500_T02116_0_M7 | 32532_TOP COATING_1300_T02546_4_M7 | mixture_change+width_long_to_short | 24060 | 24120 | 60 | 60 | 0 | 60
0 | 844 | 846 | 2 | pure_setup | 2 | 0 | 2 | 32532_TOP COATING_1300_T02546_4_M7 | 32532_투명점착_1300_T01862_4_M7 | mixture_change+operation_type_change | 25320 | 25380 | 60 | 60 | 0 | 60
0 | 860 | 923 | 63 | setup_plus_idle | 4 | 59 | 4 | 32532_투명점착_1300_T01862_4_M7 | 29059_비산점착_1500_T01792_0_M7 | mixture_change+width_short_to_long | 25800 | 27690 | 1890 | 120 | 1770 | 120
1 | 33 | 164 | 131 | pure_idle | 0 | 131 | 0 | 30151_인쇄_1500_배합X_2_M5 | 32244_인쇄_1500_배합X_1_M5 | no_setup_machine | 990 | 4920 | 3930 | 0 | 3930 | 0
1 | 169 | 183 | 14 | pure_idle | 0 | 14 | 0 | 32244_인쇄_1500_배합X_1_M5 | 32244_인쇄_1500_배합X_0_M5 | no_setup_machine | 5070 | 5490 | 420 | 0 | 420 | 0
1 | 193 | 232 | 39 | pure_idle | 0 | 39 | 0 | 31019_인쇄_1500_배합X_0_M6 | 32377_인쇄_1500_배합X_0_M6 | no_setup_machine | 5790 | 6960 | 1170 | 0 | 1170 | 0
1 | 254 | 293 | 39 | pure_idle | 0 | 39 | 0 | 32497_인쇄_1500_배합X_0_M6 | 32672_인쇄_1500_배합X_0_M6 | no_setup_machine | 7620 | 8790 | 1170 | 0 | 1170 | 0
1 | 300 | 303 | 3 | pure_idle | 0 | 3 | 0 | 32672_인쇄_1500_배합X_0_M6 | 32673_인쇄_1500_배합X_0_M6 | no_setup_machine | 9000 | 9090 | 90 | 0 | 90 | 0
1 | 334 | 337 | 3 | pure_idle | 0 | 3 | 0 | 31017_인쇄_1500_배합X_0_M6 | 31505_인쇄_1500_배합X_0_M6 | no_setup_machine | 10020 | 10110 | 90 | 0 | 90 | 0
1 | 341 | 381 | 40 | pure_idle | 0 | 40 | 0 | 31505_인쇄_1500_배합X_0_M6 | 31020_인쇄_1500_배합X_0_M6 | no_setup_machine | 10230 | 11430 | 1200 | 0 | 1200 | 0
1 | 408 | 410 | 2 | pure_idle | 0 | 2 | 0 | 31024_인쇄_1500_배합X_0_M6 | 31025_인쇄_1500_배합X_0_M6 | no_setup_machine | 12240 | 12300 | 60 | 0 | 60 | 0
1 | 427 | 444 | 17 | pure_idle | 0 | 17 | 0 | 32002_인쇄_1500_배합X_0_M6 | 31925_인쇄_1500_배합X_0_M6 | no_setup_machine | 12810 | 13320 | 510 | 0 | 510 | 0
1 | 448 | 452 | 4 | pure_idle | 0 | 4 | 0 | 31925_인쇄_1500_배합X_0_M6 | 30458_인쇄_1500_배합X_1_M6 | no_setup_machine | 13440 | 13560 | 120 | 0 | 120 | 0
1 | 461 | 464 | 3 | pure_idle | 0 | 3 | 0 | 31382_인쇄_1500_배합X_1_M6 | 30460_인쇄_1500_배합X_0_M6 | no_setup_machine | 13830 | 13920 | 90 | 0 | 90 | 0
1 | 471 | 475 | 4 | pure_idle | 0 | 4 | 0 | 30460_인쇄_1500_배합X_0_M6 | 30460_인쇄_1500_배합X_1_M6 | no_setup_machine | 14130 | 14250 | 120 | 0 | 120 | 0
1 | 499 | 577 | 78 | pure_idle | 0 | 78 | 0 | 31503_인쇄_1500_배합X_3_M6 | 32319_인쇄_1500_배합X_1_M6 | no_setup_machine | 14970 | 17310 | 2340 | 0 | 2340 | 0
1 | 579 | 590 | 11 | pure_idle | 0 | 11 | 0 | 32319_인쇄_1500_배합X_1_M6 | 32320_인쇄_1500_배합X_0_M6 | no_setup_machine | 17370 | 17700 | 330 | 0 | 330 | 0
1 | 594 | 595 | 1 | pure_idle | 0 | 1 | 0 | 32320_인쇄_1500_배합X_0_M6 | 32318_인쇄_1500_배합X_0_M6 | no_setup_machine | 17820 | 17850 | 30 | 0 | 30 | 0
1 | 737 | 741 | 4 | pure_idle | 0 | 4 | 0 | 31361_인쇄_1500_배합X_0_M7 | 31652_인쇄_1500_배합X_0_M7 | no_setup_machine | 22110 | 22230 | 120 | 0 | 120 | 0
1 | 746 | 758 | 12 | pure_idle | 0 | 12 | 0 | 31652_인쇄_1500_배합X_0_M7 | 32225_인쇄_1500_배합X_0_M6 | no_setup_machine | 22380 | 22740 | 360 | 0 | 360 | 0
1 | 769 | 770 | 1 | pure_idle | 0 | 1 | 0 | 31798_인쇄_1500_배합X_0_M7 | 31800_인쇄_1500_배합X_0_M7 | no_setup_machine | 23070 | 23100 | 30 | 0 | 30 | 0
1 | 802 | 804 | 2 | pure_idle | 0 | 2 | 0 | 32017_인쇄_1500_배합X_0_M7 | 31600_인쇄_1500_배합X_0_M7 | no_setup_machine | 24060 | 24120 | 60 | 0 | 60 | 0
1 | 812 | 836 | 24 | pure_idle | 0 | 24 | 0 | 31600_인쇄_1500_배합X_0_M7 | 31737_인쇄_1500_배합X_0_M7 | no_setup_machine | 24360 | 25080 | 720 | 0 | 720 | 0
1 | 840 | 841 | 1 | pure_idle | 0 | 1 | 0 | 31737_인쇄_1500_배합X_0_M7 | 31738_인쇄_1500_배합X_0_M7 | no_setup_machine | 25200 | 25230 | 30 | 0 | 30 | 0
1 | 891 | 894 | 3 | pure_idle | 0 | 3 | 0 | 32267_인쇄_1500_배합X_0_M7 | 32672_인쇄_1500_배합X_0_M7 | no_setup_machine | 26730 | 26820 | 90 | 0 | 90 | 0
1 | 912 | 943 | 31 | pure_idle | 0 | 31 | 0 | 32700_인쇄_1500_배합X_0_M7 | 31023_인쇄_1500_배합X_0_M7 | no_setup_machine | 27360 | 28290 | 930 | 0 | 930 | 0
1 | 955 | 971 | 16 | pure_idle | 0 | 16 | 0 | 32316_인쇄_1500_배합X_0_M7 | 32221_인쇄_1500_배합X_0_M7 | no_setup_machine | 28650 | 29130 | 480 | 0 | 480 | 0
2 | 5 | 9 | 4 | pure_setup | 4 | 0 | 4 | 30151_안료접착_1500_T02159_2_M5 | 31539_염료점착_1500_T02299_1_M5 | mixture_change+operation_type_change | 150 | 270 | 120 | 120 | 0 | 120
2 | 57 | 61 | 4 | pure_setup | 4 | 0 | 4 | 31539_염료점착_1500_T02299_2_M5 | 31539_염료점착_1300_T02299_4_M5 | width_long_to_short | 1710 | 1830 | 120 | 120 | 0 | 120
2 | 76 | 80 | 4 | pure_setup | 4 | 0 | 4 | 31539_염료점착_1300_T02299_4_M5 | 31540_염료점착_1500_T02296_1_M5 | mixture_change+width_short_to_long | 2280 | 2400 | 120 | 120 | 0 | 120
2 | 110 | 114 | 4 | pure_setup | 4 | 0 | 4 | 31540_염료점착_1500_T02296_2_M5 | 31541_염료점착_1500_T02300_1_M5 | mixture_change | 3300 | 3420 | 120 | 120 | 0 | 120
2 | 126 | 130 | 4 | pure_setup | 4 | 0 | 4 | 31541_염료점착_1500_T02300_2_M5 | 31864_염료점착_1500_T02515_1_M5 | mixture_change | 3780 | 3900 | 120 | 120 | 0 | 120
2 | 145 | 149 | 4 | pure_setup | 4 | 0 | 4 | 31864_염료점착_1500_T02515_2_M5 | 32244_안료접착_1500_T02510_1_M5 | mixture_change+operation_type_change | 4350 | 4470 | 120 | 120 | 0 | 120
2 | 157 | 161 | 4 | pure_setup | 4 | 0 | 4 | 32244_안료접착_1500_T02510_0_M5 | 31019_안료접착_1500_T02038_0_M6 | mixture_change | 4710 | 4830 | 120 | 120 | 0 | 120
2 | 168 | 172 | 4 | pure_setup | 4 | 0 | 4 | 31019_안료접착_1500_T02038_0_M6 | 26193_투명점착_1500_T01786_0_M6 | mixture_change+operation_type_change | 5040 | 5160 | 120 | 120 | 0 | 120
2 | 178 | 182 | 4 | pure_setup | 4 | 0 | 4 | 26193_투명점착_1500_T01786_0_M6 | 28732_투명접착_1500_WRF065_0_M6 | mixture_change | 5340 | 5460 | 120 | 120 | 0 | 120
2 | 188 | 192 | 4 | pure_setup | 4 | 0 | 4 | 28732_투명점착_1500_WRF065_0_M6 | 32377_안료접착_1500_T02173_0_M6 | mixture_change+operation_type_change | 5640 | 5760 | 120 | 120 | 0 | 120
2 | 197 | 201 | 4 | pure_setup | 4 | 0 | 4 | 32377_안료접착_1500_T02173_0_M6 | 32378_안료접착_1500_T02174_0_M6 | mixture_change | 5910 | 6030 | 120 | 120 | 0 | 120
2 | 207 | 211 | 4 | pure_setup | 4 | 0 | 4 | 32378_안료접착_1500_T02174_0_M6 | 32495_안료접착_1500_T02083_0_M6 | mixture_change | 6210 | 6330 | 120 | 120 | 0 | 120
2 | 214 | 218 | 4 | pure_setup | 4 | 0 | 4 | 32495_안료접착_1500_T02083_0_M6 | 32497_안료접착_1500_W2028_0_M6 | mixture_change | 6420 | 6540 | 120 | 120 | 0 | 120
2 | 221 | 225 | 4 | pure_setup | 4 | 0 | 4 | 32497_안료접착_1500_W2028_0_M6 | 32672_안료접착_1500_T02383_0_M6 | mixture_change | 6630 | 6750 | 120 | 120 | 0 | 120
2 | 231 | 235 | 4 | pure_setup | 4 | 0 | 4 | 32672_안료접착_1500_T02383_0_M6 | 32673_안료접착_1500_T02384_0_M6 | mixture_change | 6930 | 7050 | 120 | 120 | 0 | 120
2 | 238 | 242 | 4 | pure_setup | 4 | 0 | 4 | 32673_안료접착_1500_T02384_0_M6 | 32674_안료접착_1500_T02385_0_M6 | mixture_change | 7140 | 7260 | 120 | 120 | 0 | 120
2 | 245 | 249 | 4 | pure_setup | 4 | 0 | 4 | 32674_안료접착_1500_T02385_0_M6 | 32688_안료접착_1500_T02417_0_M6 | mixture_change | 7350 | 7470 | 120 | 120 | 0 | 120
2 | 252 | 256 | 4 | pure_setup | 4 | 0 | 4 | 32688_안료접착_1500_T02417_0_M6 | 32689_안료접착_1500_T02418_0_M6 | mixture_change | 7560 | 7680 | 120 | 120 | 0 | 120
2 | 262 | 266 | 4 | pure_setup | 4 | 0 | 4 | 32689_안료접착_1500_T02418_0_M6 | 32694_안료접착_1500_T02422_0_M6 | mixture_change | 7860 | 7980 | 120 | 120 | 0 | 120
2 | 269 | 273 | 4 | pure_setup | 4 | 0 | 4 | 32694_안료접착_1500_T02422_0_M6 | 32695_안료접착_1500_T02416_0_M6 | mixture_change | 8070 | 8190 | 120 | 120 | 0 | 120
2 | 276 | 280 | 4 | pure_setup | 4 | 0 | 4 | 32695_안료접착_1500_T02416_0_M6 | 31017_안료접착_1500_T02031_0_M6 | mixture_change | 8280 | 8400 | 120 | 120 | 0 | 120
2 | 283 | 287 | 4 | pure_setup | 4 | 0 | 4 | 31017_안료접착_1500_T02031_0_M6 | 31505_안료접착_1500_T02093_0_M6 | mixture_change | 8490 | 8610 | 120 | 120 | 0 | 120
2 | 290 | 294 | 4 | pure_setup | 4 | 0 | 4 | 31505_안료접착_1500_T02093_0_M6 | 31020_안료접착_1500_T02228_0_M6 | mixture_change | 8700 | 8820 | 120 | 120 | 0 | 120
2 | 301 | 305 | 4 | pure_setup | 4 | 0 | 4 | 31020_안료접착_1500_T02228_0_M6 | 31021_안료접착_1500_T02229_0_M6 | mixture_change | 9030 | 9150 | 120 | 120 | 0 | 120
2 | 311 | 315 | 4 | pure_setup | 4 | 0 | 4 | 31021_안료접착_1500_T02229_0_M6 | 31024_안료접착_1500_T02118_0_M6 | mixture_change | 9330 | 9450 | 120 | 120 | 0 | 120
2 | 322 | 326 | 4 | pure_setup | 4 | 0 | 4 | 31024_안료접착_1500_T02118_0_M6 | 31025_안료접착_1500_T02119_0_M6 | mixture_change | 9660 | 9780 | 120 | 120 | 0 | 120
2 | 332 | 336 | 4 | pure_setup | 4 | 0 | 4 | 31025_안료접착_1500_T02119_0_M6 | 31026_안료접착_1500_T02372_0_M6 | mixture_change | 9960 | 10080 | 120 | 120 | 0 | 120
2 | 339 | 343 | 4 | pure_setup | 4 | 0 | 4 | 31026_안료접착_1500_T02372_0_M6 | 31925_안료접착_1500_T02405_0_M6 | mixture_change | 10170 | 10290 | 120 | 120 | 0 | 120
2 | 347 | 351 | 4 | pure_setup | 4 | 0 | 4 | 31925_안료접착_1500_T02405_0_M6 | 32002_안료접착_1500_T02441_0_M6 | mixture_change | 10410 | 10530 | 120 | 120 | 0 | 120
2 | 359 | 363 | 4 | pure_setup | 4 | 0 | 4 | 32002_안료접착_1500_T02441_0_M6 | 30458_안료접착_1500_T02158_1_M6 | mixture_change | 10770 | 10890 | 120 | 120 | 0 | 120
2 | 368 | 372 | 4 | pure_setup | 4 | 0 | 4 | 30458_안료접착_1500_T02158_3_M6 | 30460_안료접착_1500_T02020_0_M6 | mixture_change | 11040 | 11160 | 120 | 120 | 0 | 120
2 | 390 | 394 | 4 | pure_setup | 4 | 0 | 4 | 30460_안료접착_1500_T02020_1_M6 | 31382_안료접착_1500_T02028_0_M6 | mixture_change | 11700 | 11820 | 120 | 120 | 0 | 120
2 | 396 | 400 | 4 | pure_setup | 4 | 0 | 4 | 31382_안료접착_1500_T02028_1_M6 | 31503_안료접착_1500_T02027_0_M6 | mixture_change | 11880 | 12000 | 120 | 120 | 0 | 120
2 | 405 | 409 | 4 | pure_setup | 4 | 0 | 4 | 31503_안료접착_1500_T02027_3_M6 | 30148_IR접착_1500_T02542_0_M6 | mixture_change | 12150 | 12270 | 120 | 120 | 0 | 120
2 | 411 | 415 | 4 | pure_setup | 4 | 0 | 4 | 30148_IR접착_1500_T02542_0_M6 | 32320_안료접착_1500_T01696_0_M6 | mixture_change | 12330 | 12450 | 120 | 120 | 0 | 120
2 | 418 | 422 | 4 | pure_setup | 4 | 0 | 4 | 32320_안료접착_1500_T01696_0_M6 | 32318_안료접착_1500_T02532_0_M6 | mixture_change | 12540 | 12660 | 120 | 120 | 0 | 120
2 | 427 | 431 | 4 | pure_setup | 4 | 0 | 4 | 32318_안료접착_1500_T02532_0_M6 | 32318_안료접착_1000_T02532_1_M6 | width_long_to_short | 12810 | 12930 | 120 | 120 | 0 | 120
2 | 434 | 438 | 4 | pure_setup | 4 | 0 | 4 | 32318_안료접착_1000_T02532_1_M6 | 32717_안료접착_1500_T02537_0_M6 | mixture_change+width_short_to_long | 13020 | 13140 | 120 | 120 | 0 | 120
2 | 442 | 446 | 4 | pure_setup | 4 | 0 | 4 | 32717_안료접착_1500_T02537_0_M6 | 32718_안료접착_1500_T02536_0_M6 | mixture_change | 13260 | 13380 | 120 | 120 | 0 | 120
2 | 450 | 454 | 4 | pure_setup | 4 | 0 | 4 | 32718_안료접착_1500_T02536_0_M6 | 32719_안료접착_1500_T02535_0_M6 | mixture_change | 13500 | 13620 | 120 | 120 | 0 | 120
2 | 458 | 462 | 4 | pure_setup | 4 | 0 | 4 | 32719_안료접착_1500_T02535_0_M6 | 32304_안료접착_1500_T02521_1_M6 | mixture_change | 13740 | 13860 | 120 | 120 | 0 | 120
2 | 464 | 468 | 4 | pure_setup | 4 | 0 | 4 | 32304_안료접착_1500_T02521_1_M6 | 32305_안료접착_1500_T02522_0_M6 | mixture_change | 13920 | 14040 | 120 | 120 | 0 | 120
2 | 471 | 475 | 4 | pure_setup | 4 | 0 | 4 | 32305_안료접착_1500_T02522_0_M6 | 32305_안료접착_1000_T02522_1_M6 | width_long_to_short | 14130 | 14250 | 120 | 120 | 0 | 120
2 | 479 | 483 | 4 | pure_setup | 4 | 0 | 4 | 32305_안료접착_1000_T02522_1_M6 | 32306_안료접착_1500_T02534_0_M6 | mixture_change+width_short_to_long | 14370 | 14490 | 120 | 120 | 0 | 120
2 | 486 | 490 | 4 | pure_setup | 4 | 0 | 4 | 32306_안료접착_1500_T02534_0_M6 | 32306_안료접착_1000_T02534_1_M6 | width_long_to_short | 14580 | 14700 | 120 | 120 | 0 | 120
2 | 496 | 500 | 4 | pure_setup | 4 | 0 | 4 | 32306_안료접착_1000_T02534_1_M6 | 32307_안료접착_1500_T02524_0_M6 | mixture_change+width_short_to_long | 14880 | 15000 | 120 | 120 | 0 | 120
2 | 508 | 512 | 4 | pure_setup | 4 | 0 | 4 | 32307_안료접착_1500_T02524_1_M6 | 32310_안료접착_1500_T01748_0_M6 | mixture_change | 15240 | 15360 | 120 | 120 | 0 | 120
2 | 515 | 519 | 4 | pure_setup | 4 | 0 | 4 | 32310_안료접착_1500_T01748_0_M6 | 32310_안료접착_1000_T01748_1_M6 | width_long_to_short | 15450 | 15570 | 120 | 120 | 0 | 120
2 | 526 | 530 | 4 | pure_setup | 4 | 0 | 4 | 32310_안료접착_1000_T01748_1_M6 | 32311_안료접착_1500_T01687_0_M6 | mixture_change+width_short_to_long | 15780 | 15900 | 120 | 120 | 0 | 120
2 | 536 | 540 | 4 | pure_setup | 4 | 0 | 4 | 32311_안료접착_1500_T01687_1_M6 | 32312_안료접착_1500_T01688_0_M6 | mixture_change | 16080 | 16200 | 120 | 120 | 0 | 120
2 | 545 | 549 | 4 | pure_setup | 4 | 0 | 4 | 32312_안료접착_1500_T01688_1_M6 | 32313_안료접착_1500_T01689_0_M6 | mixture_change | 16350 | 16470 | 120 | 120 | 0 | 120
2 | 555 | 559 | 4 | pure_setup | 4 | 0 | 4 | 32313_안료접착_1500_T01689_1_M6 | 32314_안료접착_1500_T01690_0_M6 | mixture_change | 16650 | 16770 | 120 | 120 | 0 | 120
2 | 564 | 568 | 4 | pure_setup | 4 | 0 | 4 | 32314_안료접착_1500_T01690_1_M6 | 32319_안료접착_1500_T02531_0_M6 | mixture_change | 16920 | 17040 | 120 | 120 | 0 | 120
2 | 573 | 577 | 4 | pure_setup | 4 | 0 | 4 | 32319_안료접착_1500_T02531_1_M6 | 32303_안료접착_1000_T01684_1_M6 | mixture_change+width_long_to_short | 17190 | 17310 | 120 | 120 | 0 | 120
2 | 581 | 585 | 4 | pure_setup | 4 | 0 | 4 | 32303_안료접착_1000_T01684_1_M6 | 25280_비산점착_1500_W1558_0_M6 | mixture_change+operation_type_change+width_short_to_long | 17430 | 17550 | 120 | 120 | 0 | 120
2 | 593 | 597 | 4 | pure_setup | 4 | 0 | 4 | 25280_비산접착(1차)_1500_W1558_0_M6 | 25280_비산접착(2차)_1500_T0897_0_M6 | mixture_change | 17790 | 17910 | 120 | 120 | 0 | 120
2 | 601 | 605 | 4 | pure_setup | 4 | 0 | 4 | 25280_비산접착(2차)_1500_T0897_0_M6 | 32222_안료접착_1500_T02148_0_M6 | mixture_change+operation_type_change | 18030 | 18150 | 120 | 120 | 0 | 120
2 | 622 | 626 | 4 | pure_setup | 4 | 0 | 4 | 32222_안료접착_1500_T02148_0_M6 | 32225_안료접착_1500_T02142_0_M6 | mixture_change | 18660 | 18780 | 120 | 120 | 0 | 120
2 | 632 | 636 | 4 | pure_setup | 4 | 0 | 4 | 32225_안료접착_1500_T02142_0_M6 | 30458_안료접착_1500_T02158_0_M7 | mixture_change | 18960 | 19080 | 120 | 120 | 0 | 120
2 | 639 | 643 | 4 | pure_setup | 4 | 0 | 4 | 30458_안료접착_1500_T02158_0_M7 | 31361_안료접착_1500_T02403_0_M7 | mixture_change | 19170 | 19290 | 120 | 120 | 0 | 120
2 | 646 | 650 | 4 | pure_setup | 4 | 0 | 4 | 31361_안료접착_1500_T02403_0_M7 | 31600_안료접착_1500_T02295_0_M7 | mixture_change | 19380 | 19500 | 120 | 120 | 0 | 120
2 | 658 | 662 | 4 | pure_setup | 4 | 0 | 4 | 31600_안료접착_1500_T02295_0_M7 | 31652_안료접착_1500_T02303_0_M7 | mixture_change | 19740 | 19860 | 120 | 120 | 0 | 120
2 | 667 | 671 | 4 | pure_setup | 4 | 0 | 4 | 31652_안료접착_1500_T02303_0_M7 | 31737_안료접착_1500_T02016_0_M7 | mixture_change | 20010 | 20130 | 120 | 120 | 0 | 120
2 | 675 | 679 | 4 | pure_setup | 4 | 0 | 4 | 31737_안료접착_1500_T02016_0_M7 | 31738_안료접착_1500_T02363_0_M7 | mixture_change | 20250 | 20370 | 120 | 120 | 0 | 120
2 | 685 | 689 | 4 | pure_setup | 4 | 0 | 4 | 31738_안료접착_1500_T02363_0_M7 | 31739_안료접착_1500_T02364_0_M7 | mixture_change | 20550 | 20670 | 120 | 120 | 0 | 120
2 | 692 | 696 | 4 | pure_setup | 4 | 0 | 4 | 31739_안료접착_1500_T02364_0_M7 | 31798_안료접착_1500_T02014_0_M7 | mixture_change | 20760 | 20880 | 120 | 120 | 0 | 120
2 | 700 | 704 | 4 | pure_setup | 4 | 0 | 4 | 31798_안료접착_1500_T02014_0_M7 | 31800_안료접착_1500_T02126_0_M7 | mixture_change | 21000 | 21120 | 120 | 120 | 0 | 120
2 | 710 | 714 | 4 | pure_setup | 4 | 0 | 4 | 31800_안료접착_1500_T02126_0_M7 | 31802_안료접착_1500_T02015_0_M7 | mixture_change | 21300 | 21420 | 120 | 120 | 0 | 120
2 | 720 | 724 | 4 | pure_setup | 4 | 0 | 4 | 31802_안료접착_1500_T02015_0_M7 | 32016_안료접착_1500_T02318_0_M7 | mixture_change | 21600 | 21720 | 120 | 120 | 0 | 120
2 | 732 | 736 | 4 | pure_setup | 4 | 0 | 4 | 32016_안료접착_1500_T02318_0_M7 | 32017_안료접착_1500_T02319_0_M7 | mixture_change | 21960 | 22080 | 120 | 120 | 0 | 120
2 | 745 | 749 | 4 | pure_setup | 4 | 0 | 4 | 32017_안료접착_1500_T02319_0_M7 | 32260_안료접착_1500_T02186_0_M7 | mixture_change | 22350 | 22470 | 120 | 120 | 0 | 120
2 | 752 | 756 | 4 | pure_setup | 4 | 0 | 4 | 32260_안료접착_1500_T02186_0_M7 | 32261_안료접착_1500_T02185_0_M7 | mixture_change | 22560 | 22680 | 120 | 120 | 0 | 120
2 | 762 | 766 | 4 | pure_setup | 4 | 0 | 4 | 32261_안료접착_1500_T02185_0_M7 | 32262_안료접착_1500_T02131_0_M7 | mixture_change | 22860 | 22980 | 120 | 120 | 0 | 120
2 | 770 | 774 | 4 | pure_setup | 4 | 0 | 4 | 32262_안료접착_1500_T02131_0_M7 | 32264_안료접착_1500_T02219_0_M7 | mixture_change | 23100 | 23220 | 120 | 120 | 0 | 120
2 | 781 | 785 | 4 | pure_setup | 4 | 0 | 4 | 32264_안료접착_1500_T02219_0_M7 | 32266_안료접착_1500_T02500_0_M7 | mixture_change | 23430 | 23550 | 120 | 120 | 0 | 120
2 | 789 | 793 | 4 | pure_setup | 4 | 0 | 4 | 32266_안료접착_1500_T02500_0_M7 | 32267_안료접착_1500_T02555_0_M7 | mixture_change | 23670 | 23790 | 120 | 120 | 0 | 120
2 | 800 | 804 | 4 | pure_setup | 4 | 0 | 4 | 32267_안료접착_1500_T02555_0_M7 | 32672_안료접착_1500_T02383_0_M7 | mixture_change | 24000 | 24120 | 120 | 120 | 0 | 120
2 | 809 | 813 | 4 | pure_setup | 4 | 0 | 4 | 32672_안료접착_1500_T02383_0_M7 | 32674_안료접착_1500_T02385_0_M7 | mixture_change | 24270 | 24390 | 120 | 120 | 0 | 120
2 | 816 | 820 | 4 | pure_setup | 4 | 0 | 4 | 32674_안료접착_1500_T02385_0_M7 | 32692_안료접착_1500_T02426_0_M7 | mixture_change | 24480 | 24600 | 120 | 120 | 0 | 120
2 | 823 | 827 | 4 | pure_setup | 4 | 0 | 4 | 32692_안료접착_1500_T02426_0_M7 | 32700_안료접착_1500_T02391_0_M7 | mixture_change | 24690 | 24810 | 120 | 120 | 0 | 120
2 | 830 | 834 | 4 | pure_setup | 4 | 0 | 4 | 32700_안료접착_1500_T02391_0_M7 | 28731_투명접착_1500_WRF065_0_M7 | mixture_change+operation_type_change | 24900 | 25020 | 120 | 120 | 0 | 120
2 | 842 | 846 | 4 | pure_setup | 4 | 0 | 4 | 28731_투명점착_1500_WRF065_0_M7 | 31023_안료접착_1500_T02404_0_M7 | mixture_change+operation_type_change | 25260 | 25380 | 120 | 120 | 0 | 120
2 | 852 | 856 | 4 | pure_setup | 4 | 0 | 4 | 31023_안료접착_1500_T02404_0_M7 | 32221_안료접착_1500_T02147_0_M7 | mixture_change | 25560 | 25680 | 120 | 120 | 0 | 120
2 | 879 | 883 | 4 | pure_setup | 4 | 0 | 4 | 32221_안료접착_1500_T02147_0_M7 | 32316_안료접착_1500_T02539_0_M7 | mixture_change | 26370 | 26490 | 120 | 120 | 0 | 120
2 | 887 | 891 | 4 | pure_setup | 4 | 0 | 4 | 32316_안료접착_1500_T02539_0_M7 | 32730_안료접착_1500_T02493_0_M7 | mixture_change | 26610 | 26730 | 120 | 120 | 0 | 120
3 | 8 | 10 | 2 | pure_setup | 2 | 0 | 2 | 30151_MIBK SR_1500_T02149_2_M5 | 32528_유광 S/R_1300_T02149_4_M5 | width_long_to_short | 240 | 300 | 60 | 60 | 0 | 60
3 | 16 | 20 | 4 | setup_plus_idle | 2 | 2 | 2 | 32528_유광 S/R_1300_T02149_4_M5 | 30151_투명점착_1500_W2010_2_M5 | mixture_change+operation_type_change+width_short_to_long | 480 | 600 | 120 | 60 | 60 | 60
3 | 26 | 28 | 2 | pure_setup | 2 | 0 | 4 | 30151_투명점착_1500_W2010_2_M5 | 31539_유광 S/R_1500_T02149_1_M5 | mixture_change+operation_type_change | 780 | 840 | 60 | 60 | 0 | 120
3 | 37 | 39 | 2 | pure_setup | 2 | 0 | 2 | 31539_유광 S/R_1500_T02149_1_M5 | 29059_유광 S/R_1500_W1809_0_M6 | mixture_change | 1110 | 1170 | 60 | 60 | 0 | 60
3 | 51 | 57 | 6 | setup_plus_idle | 2 | 4 | 2 | 29059_유광 S/R_1500_W1809_0_M6 | 31539_유광 S/R_1500_T02149_2_M5 | mixture_change | 1530 | 1710 | 180 | 60 | 120 | 60
3 | 70 | 76 | 6 | setup_plus_idle | 2 | 4 | 2 | 31539_유광 S/R_1500_T02149_2_M5 | 31539_유광 S/R_1300_T02149_4_M5 | width_long_to_short | 2100 | 2280 | 180 | 60 | 120 | 60
3 | 83 | 85 | 2 | pure_setup | 2 | 0 | 2 | 31539_유광 S/R_1300_T02149_4_M5 | 25278_유광 S/R_1500_T02149_0_M6 | width_short_to_long | 2490 | 2550 | 60 | 60 | 0 | 60
3 | 106 | 110 | 4 | pure_idle | 0 | 4 | 0 | 31540_유광 S/R_1500_T02149_1_M5 | 31540_유광 S/R_1500_T02149_2_M5 | no_change_detected | 3180 | 3300 | 120 | 0 | 120 | 0
3 | 117 | 120 | 3 | pure_idle | 0 | 3 | 0 | 31540_유광 S/R_1500_T02149_2_M5 | 31541_유광 S/R_1500_T02149_1_M5 | no_change_detected | 3510 | 3600 | 90 | 0 | 90 | 0
3 | 124 | 126 | 2 | pure_idle | 0 | 2 | 0 | 31541_유광 S/R_1500_T02149_1_M5 | 31541_유광 S/R_1500_T02149_2_M5 | no_change_detected | 3720 | 3780 | 60 | 0 | 60 | 0
3 | 130 | 139 | 9 | setup_plus_idle | 2 | 7 | 2 | 31541_유광 S/R_1500_T02149_2_M5 | 31864_유광 S/R_1500_W1809_1_M5 | mixture_change | 3900 | 4170 | 270 | 60 | 210 | 60
3 | 149 | 154 | 5 | setup_plus_idle | 2 | 3 | 2 | 31864_유광 S/R_1500_W1809_2_M5 | 32244_ISR(하드코팅)_1500_W1818_1_M5 | mixture_change | 4470 | 4620 | 150 | 60 | 90 | 60
3 | 156 | 157 | 1 | pure_idle | 0 | 1 | 0 | 32244_ISR(하드코팅)_1500_W1818_1_M5 | 32244_ISR(하드코팅)_1500_W1818_0_M5 | no_change_detected | 4680 | 4710 | 30 | 0 | 30 | 0
3 | 159 | 161 | 2 | pure_setup | 2 | 0 | 2 | 32244_ISR(하드코팅)_1500_W1818_0_M5 | 32244_투명점착_1500_WRF065_1_M5 | mixture_change+operation_type_change | 4770 | 4830 | 60 | 60 | 0 | 60
3 | 164 | 168 | 4 | pure_setup | 4 | 0 | 4 | 32244_투명점착_1500_WRF065_1_M5 | 31019_ISR(하드코팅)_1500_W1818_0_M6 | mixture_change+operation_type_change | 4920 | 5040 | 120 | 120 | 0 | 120
3 | 177 | 181 | 4 | pure_setup | 4 | 0 | 4 | 31019_투명점착_1500_W1818_0_M6 | 32244_투명점착_1500_WRF065_0_M5 | mixture_change | 5310 | 5430 | 120 | 120 | 0 | 120
3 | 183 | 185 | 2 | pure_setup | 2 | 0 | 4 | 32244_투명점착_1500_WRF065_0_M5 | 25033_유광 S/R_1500_T02149_0_M6 | mixture_change+operation_type_change | 5490 | 5550 | 60 | 60 | 0 | 120
3 | 191 | 197 | 6 | setup_plus_idle | 2 | 4 | 2 | 28732_유광 S/R_1500_T02149_0_M6 | 32377_MIBK SR(항균)_1500_t01828_0_M6 | mixture_change | 5730 | 5910 | 180 | 60 | 120 | 60
3 | 200 | 207 | 7 | pure_idle | 0 | 7 | 0 | 32377_MIBK SR(항균)_1500_t01828_0_M6 | 32378_MIBK SR(항균)_1500_t01828_0_M6 | no_change_detected | 6000 | 6210 | 210 | 0 | 210 | 0
3 | 210 | 214 | 4 | setup_plus_idle | 2 | 2 | 2 | 32378_MIBK SR(항균)_1500_t01828_0_M6 | 32495_MIBK SR(항균)_1500_T01828_0_M6 | mixture_change | 6300 | 6420 | 120 | 60 | 60 | 60
3 | 216 | 221 | 5 | setup_plus_idle | 2 | 3 | 2 | 32495_MIBK SR(항균)_1500_T01828_0_M6 | 32497_MIBK SR(항균)_1500_t01828_0_M6 | mixture_change | 6480 | 6630 | 150 | 60 | 90 | 60
3 | 223 | 227 | 4 | setup_plus_idle | 2 | 2 | 2 | 32497_MIBK SR(항균)_1500_t01828_0_M6 | 32377_투명점착_1500_WRF065_0_M6 | mixture_change+operation_type_change | 6690 | 6810 | 120 | 60 | 60 | 60
3 | 243 | 245 | 2 | pure_setup | 2 | 0 | 4 | 32497_투명점착_1500_WRF065_0_M6 | 32672_ISR(항균)_1500_T01512_0_M6 | mixture_change+operation_type_change | 7290 | 7350 | 60 | 60 | 0 | 120
3 | 256 | 262 | 6 | pure_idle | 0 | 6 | 0 | 32674_ISR(항균)_1500_T01512_0_M6 | 32689_ISR(항균)_1500_T01512_0_M6 | no_change_detected | 7680 | 7860 | 180 | 0 | 180 | 0
3 | 267 | 269 | 2 | pure_idle | 0 | 2 | 0 | 32689_ISR(항균)_1500_T01512_0_M6 | 32694_ISR(항균)_1500_T01512_0_M6 | no_change_detected | 8010 | 8070 | 60 | 0 | 60 | 0
3 | 272 | 276 | 4 | pure_idle | 0 | 4 | 0 | 32694_ISR(항균)_1500_T01512_0_M6 | 32695_ISR(항균)_1500_T01512_0_M6 | no_change_detected | 8160 | 8280 | 120 | 0 | 120 | 0
3 | 279 | 281 | 2 | pure_setup | 2 | 0 | 2 | 32695_ISR(항균)_1500_T01512_0_M6 | 32688_ISR(항균)_1500_W2026_0_M6 | mixture_change | 8370 | 8430 | 60 | 60 | 0 | 60
3 | 284 | 288 | 4 | setup_plus_idle | 2 | 2 | 2 | 32688_ISR(항균)_1500_W2026_0_M6 | 32672_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 8520 | 8640 | 120 | 60 | 60 | 60
3 | 296 | 300 | 4 | pure_setup | 4 | 0 | 4 | 32674_투명점착_1500_T01750_0_M6 | 32673_투명점착_1500_WRF065_0_M6 | mixture_change | 8880 | 9000 | 120 | 120 | 0 | 120
3 | 317 | 319 | 2 | pure_setup | 2 | 0 | 4 | 32695_투명점착_1500_WRF065_0_M6 | 31017_MIBK SR_1500_T02149_0_M6 | mixture_change+operation_type_change | 9510 | 9570 | 60 | 60 | 0 | 120
3 | 323 | 327 | 4 | setup_plus_idle | 2 | 2 | 2 | 31505_MIBK SR_1500_T02149_0_M6 | 31017_투명점착_1500_W1818_0_M6 | mixture_change+operation_type_change | 9690 | 9810 | 120 | 60 | 60 | 60
3 | 330 | 334 | 4 | pure_setup | 4 | 0 | 4 | 31017_투명점착_1500_W1818_0_M6 | 31505_투명점착_1500_WRF065_0_M6 | mixture_change | 9900 | 10020 | 120 | 120 | 0 | 120
3 | 337 | 339 | 2 | pure_setup | 2 | 0 | 4 | 31505_투명점착_1500_WRF065_0_M6 | 31020_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change+operation_type_change | 10110 | 10170 | 60 | 60 | 0 | 120
3 | 354 | 359 | 5 | pure_idle | 0 | 5 | 0 | 31026_ISR(하드코팅)_1500_T02150_0_M6 | 32002_ISR(하드코팅)_1500_T02150_0_M6 | no_change_detected | 10620 | 10770 | 150 | 0 | 150 | 0
3 | 363 | 365 | 2 | pure_setup | 2 | 0 | 2 | 32002_ISR(하드코팅)_1500_T02150_0_M6 | 31024_ISR(하드코팅)_1500_W1818_0_M6 | mixture_change | 10890 | 10950 | 60 | 60 | 0 | 60
3 | 370 | 374 | 4 | setup_plus_idle | 2 | 2 | 2 | 31024_ISR(하드코팅)_1500_W1818_0_M6 | 31020_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 11100 | 11220 | 120 | 60 | 60 | 60
3 | 401 | 405 | 4 | pure_setup | 4 | 0 | 4 | 32002_투명점착_1500_T01750_0_M6 | 31025_투명점착_1500_W2026_0_M6 | mixture_change | 12030 | 12150 | 120 | 120 | 0 | 120
3 | 410 | 412 | 2 | pure_setup | 2 | 0 | 4 | 31025_투명점착_1500_W2026_0_M6 | 31925_MIBK SR_1500_T02149_0_M6 | mixture_change+operation_type_change | 12300 | 12360 | 60 | 60 | 0 | 120
3 | 433 | 435 | 2 | pure_setup | 2 | 0 | 2 | 31503_MIBK SR_1500_T02149_3_M6 | 31382_MIBK SR_1500_W1817_0_M6 | mixture_change | 12990 | 13050 | 60 | 60 | 0 | 60
3 | 437 | 441 | 4 | setup_plus_idle | 2 | 2 | 2 | 31382_MIBK SR_1500_W1817_1_M6 | 31925_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 13110 | 13230 | 120 | 60 | 60 | 60
3 | 444 | 448 | 4 | pure_setup | 4 | 0 | 4 | 31925_투명점착_1500_T01750_0_M6 | 30458_투명점착_1500_W2010_1_M6 | mixture_change | 13320 | 13440 | 120 | 120 | 0 | 120
3 | 455 | 459 | 4 | pure_setup | 4 | 0 | 4 | 31382_투명점착_1500_W2010_1_M6 | 30460_투명점착_1500_WRF065_0_M6 | mixture_change | 13650 | 13770 | 120 | 120 | 0 | 120
3 | 480 | 482 | 2 | pure_setup | 2 | 0 | 4 | 31503_투명점착_1500_WRF065_3_M6 | 30148_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change+operation_type_change | 14400 | 14460 | 60 | 60 | 0 | 120
3 | 483 | 485 | 2 | pure_setup | 2 | 0 | 2 | 30148_ISR(하드코팅)_1500_T02150_0_M6 | 32320_ISR(하드코팅)_1500_W1818_0_M6 | mixture_change | 14490 | 14550 | 60 | 60 | 0 | 60
3 | 493 | 495 | 2 | pure_setup | 2 | 0 | 2 | 32318_ISR(하드코팅)_1500_W1818_0_M6 | 32318_ISR(하드코팅)_1000_W1818_1_M6 | width_long_to_short | 14790 | 14850 | 60 | 60 | 0 | 60
3 | 497 | 499 | 2 | pure_setup | 2 | 0 | 2 | 32318_ISR(하드코팅)_1000_W1818_1_M6 | 32304_ISR(하드코팅)_1500_T02150_1_M6 | mixture_change+width_short_to_long | 14910 | 14970 | 60 | 60 | 0 | 60
3 | 507 | 508 | 1 | pure_idle | 0 | 1 | 0 | 32307_ISR(하드코팅)_1500_T02150_0_M6 | 32307_ISR(하드코팅)_1500_T02150_1_M6 | no_change_detected | 15210 | 15240 | 30 | 0 | 30 | 0
3 | 511 | 515 | 4 | pure_idle | 0 | 4 | 0 | 32307_ISR(하드코팅)_1500_T02150_1_M6 | 32310_ISR(하드코팅)_1500_T02150_0_M6 | no_change_detected | 15330 | 15450 | 120 | 0 | 120 | 0
3 | 517 | 519 | 2 | pure_setup | 2 | 0 | 2 | 32310_ISR(하드코팅)_1500_T02150_0_M6 | 32305_ISR(하드코팅)_1000_T02150_1_M6 | width_long_to_short | 15510 | 15570 | 60 | 60 | 0 | 60
3 | 525 | 526 | 1 | pure_idle | 0 | 1 | 0 | 32306_ISR(하드코팅)_1000_T02150_1_M6 | 32310_ISR(하드코팅)_1000_T02150_1_M6 | no_change_detected | 15750 | 15780 | 30 | 0 | 30 | 0
3 | 531 | 533 | 2 | pure_setup | 2 | 0 | 2 | 32310_ISR(하드코팅)_1000_T02150_1_M6 | 32311_ISR(하드코팅)_1500_W1818_0_M6 | mixture_change+width_short_to_long | 15930 | 15990 | 60 | 60 | 0 | 60
3 | 535 | 536 | 1 | pure_idle | 0 | 1 | 0 | 32311_ISR(하드코팅)_1500_W1818_0_M6 | 32311_ISR(하드코팅)_1500_W1818_1_M6 | no_change_detected | 16050 | 16080 | 30 | 0 | 30 | 0
3 | 538 | 543 | 5 | setup_plus_idle | 2 | 3 | 2 | 32311_ISR(하드코팅)_1500_W1818_1_M6 | 32312_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change | 16140 | 16290 | 150 | 60 | 90 | 60
3 | 546 | 548 | 2 | pure_setup | 2 | 0 | 2 | 32312_ISR(하드코팅)_1500_T02150_1_M6 | 32717_MIBK SR_1500_T02149_0_M6 | mixture_change | 16380 | 16440 | 60 | 60 | 0 | 60
3 | 550 | 552 | 2 | pure_setup | 2 | 0 | 2 | 32717_MIBK SR_1500_T02149_0_M6 | 32313_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change | 16500 | 16560 | 60 | 60 | 0 | 60
3 | 554 | 555 | 1 | pure_idle | 0 | 1 | 0 | 32313_ISR(하드코팅)_1500_T02150_0_M6 | 32313_ISR(하드코팅)_1500_T02150_1_M6 | no_change_detected | 16620 | 16650 | 30 | 0 | 30 | 0
3 | 557 | 562 | 5 | pure_idle | 0 | 5 | 0 | 32313_ISR(하드코팅)_1500_T02150_1_M6 | 32314_ISR(하드코팅)_1500_T02150_0_M6 | no_change_detected | 16710 | 16860 | 150 | 0 | 150 | 0
3 | 565 | 567 | 2 | pure_setup | 2 | 0 | 2 | 32314_ISR(하드코팅)_1500_T02150_1_M6 | 32718_MIBK SR_1500_T02149_0_M6 | mixture_change | 16950 | 17010 | 60 | 60 | 0 | 60
3 | 569 | 571 | 2 | pure_setup | 2 | 0 | 2 | 32718_MIBK SR_1500_T02149_0_M6 | 32319_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change | 17070 | 17130 | 60 | 60 | 0 | 60
3 | 574 | 576 | 2 | pure_setup | 2 | 0 | 2 | 32319_ISR(하드코팅)_1500_T02150_1_M6 | 32319_투명점착_1500_WRF065_1_M6 | mixture_change+operation_type_change | 17220 | 17280 | 60 | 60 | 0 | 60
3 | 577 | 581 | 4 | pure_setup | 4 | 0 | 4 | 32319_투명점착_1500_WRF065_1_M6 | 32303_ISR(하드코팅)_1000_T02150_1_M6 | mixture_change+operation_type_change+width_long_to_short | 17310 | 17430 | 120 | 120 | 0 | 120
3 | 583 | 585 | 2 | pure_setup | 2 | 0 | 2 | 32303_ISR(하드코팅)_1000_T02150_1_M6 | 32304_투명점착_1500_WRF065_1_M6 | mixture_change+operation_type_change+width_short_to_long | 17490 | 17550 | 60 | 60 | 0 | 60
3 | 627 | 629 | 2 | pure_setup | 2 | 0 | 2 | 32319_투명점착_1500_WRF065_0_M6 | 32303_투명점착_1000_WRF065_1_M6 | width_long_to_short | 18810 | 18870 | 60 | 60 | 0 | 60
3 | 648 | 650 | 2 | pure_setup | 2 | 0 | 4 | 32318_투명점착_1000_WRF065_1_M6 | 32719_MIBK SR_1500_T02149_0_M6 | mixture_change+operation_type_change+width_short_to_long | 19440 | 19500 | 60 | 60 | 0 | 120
3 | 652 | 656 | 4 | setup_plus_idle | 2 | 2 | 2 | 32719_MIBK SR_1500_T02149_0_M6 | 32717_투명점착_1500_WRF065_0_M6 | mixture_change+operation_type_change | 19560 | 19680 | 120 | 60 | 60 | 60
3 | 665 | 669 | 4 | pure_setup | 4 | 0 | 4 | 32719_투명점착_1500_WRF065_0_M6 | 32222_투명점착_1500_T01750_0_M6 | mixture_change | 19950 | 20070 | 120 | 120 | 0 | 120
3 | 684 | 688 | 4 | pure_setup | 4 | 0 | 4 | 32222_투명점착_1500_T01750_0_M6 | 30458_투명점착_1500_W2010_0_M7 | mixture_change | 20520 | 20640 | 120 | 120 | 0 | 120
3 | 694 | 696 | 2 | pure_setup | 2 | 0 | 4 | 31361_투명점착_1500_W2010_0_M7 | 32225_MIBK SR_1500_T02149_0_M6 | mixture_change+operation_type_change | 20820 | 20880 | 60 | 60 | 0 | 120
3 | 701 | 703 | 2 | pure_setup | 2 | 0 | 2 | 31652_MIBK SR_1500_T02149_0_M7 | 31798_MIBK SR_1500_W1817_0_M7 | mixture_change | 21030 | 21090 | 60 | 60 | 0 | 60
3 | 705 | 710 | 5 | setup_plus_idle | 2 | 3 | 2 | 31798_MIBK SR_1500_W1817_0_M7 | 31800_MIBK SR_1500_T02149_0_M7 | mixture_change | 21150 | 21300 | 150 | 60 | 90 | 60
3 | 714 | 716 | 2 | pure_setup | 2 | 0 | 2 | 31800_MIBK SR_1500_T02149_0_M7 | 31737_ISR(하드코팅)_1500_T02150_0_M7 | mixture_change | 21420 | 21480 | 60 | 60 | 0 | 60
3 | 718 | 720 | 2 | pure_setup | 2 | 0 | 2 | 31737_ISR(하드코팅)_1500_T02150_0_M7 | 31802_MIBK SR_1500_T02149_0_M7 | mixture_change | 21540 | 21600 | 60 | 60 | 0 | 60
3 | 724 | 726 | 2 | pure_setup | 2 | 0 | 2 | 31802_MIBK SR_1500_T02149_0_M7 | 31738_ISR(하드코팅)_1500_T02150_0_M7 | mixture_change | 21720 | 21780 | 60 | 60 | 0 | 60
3 | 730 | 732 | 2 | pure_setup | 2 | 0 | 2 | 31738_ISR(하드코팅)_1500_T02150_0_M7 | 32016_MIBK SR_1500_T02149_0_M7 | mixture_change | 21900 | 21960 | 60 | 60 | 0 | 60
3 | 736 | 738 | 2 | pure_setup | 2 | 0 | 2 | 32016_MIBK SR_1500_T02149_0_M7 | 31652_투명점착_1500_WRF065_0_M7 | mixture_change+operation_type_change | 22080 | 22140 | 60 | 60 | 0 | 60
3 | 741 | 745 | 4 | pure_setup | 4 | 0 | 4 | 31652_투명점착_1500_WRF065_0_M7 | 32017_MIBK SR_1500_T02149_0_M7 | mixture_change+operation_type_change | 22230 | 22350 | 120 | 120 | 0 | 120
3 | 749 | 753 | 4 | setup_plus_idle | 2 | 2 | 2 | 32017_MIBK SR_1500_T02149_0_M7 | 32225_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 22470 | 22590 | 120 | 60 | 60 | 60
3 | 758 | 762 | 4 | pure_setup | 4 | 0 | 4 | 32225_투명점착_1500_T01750_0_M6 | 31798_투명점착_1500_WRF065_0_M7 | mixture_change | 22740 | 22860 | 120 | 120 | 0 | 120
3 | 787 | 789 | 2 | pure_setup | 2 | 0 | 4 | 32017_투명점착_1500_WRF065_0_M7 | 31600_WSR 코팅_1500_W1912_0_M7 | mixture_change+operation_type_change | 23610 | 23670 | 60 | 60 | 0 | 120
3 | 794 | 798 | 4 | setup_plus_idle | 2 | 2 | 2 | 31600_WSR 코팅_1500_W1912_0_M7 | 31600_투명점착_1500_WRF065_0_M7 | mixture_change+operation_type_change | 23820 | 23940 | 120 | 60 | 60 | 60
3 | 804 | 806 | 2 | pure_setup | 2 | 0 | 4 | 31600_투명점착_1500_WRF065_0_M7 | 32262_ISR(하드코팅)_1500_T02150_0_M7 | mixture_change+operation_type_change | 24120 | 24180 | 60 | 60 | 0 | 120
3 | 813 | 815 | 2 | pure_setup | 2 | 0 | 2 | 32264_ISR(하드코팅)_1500_T02150_0_M7 | 31739_ISR(하드코팅)_1500_W1818_0_M7 | mixture_change | 24390 | 24450 | 60 | 60 | 0 | 60
3 | 829 | 833 | 4 | setup_plus_idle | 2 | 2 | 2 | 32267_ISR(하드코팅)_1500_W1818_0_M7 | 31737_투명점착_1500_WRF065_0_M7 | mixture_change+operation_type_change | 24870 | 24990 | 120 | 60 | 60 | 60
3 | 871 | 873 | 2 | pure_setup | 2 | 0 | 4 | 32267_투명점착_1500_WRF065_0_M7 | 32672_ISR(항균)_1500_T01512_0_M7 | mixture_change+operation_type_change | 26130 | 26190 | 60 | 60 | 0 | 120
3 | 886 | 890 | 4 | setup_plus_idle | 2 | 2 | 2 | 32700_ISR(항균)_1500_T01512_0_M7 | 32672_투명점착_1500_T01750_0_M7 | mixture_change+operation_type_change | 26580 | 26700 | 120 | 60 | 60 | 60
3 | 897 | 901 | 4 | pure_setup | 4 | 0 | 4 | 32674_투명점착_1500_T01750_0_M7 | 32692_투명점착_1500_WRF065_0_M7 | mixture_change | 26910 | 27030 | 120 | 120 | 0 | 120
3 | 907 | 909 | 2 | pure_setup | 2 | 0 | 4 | 32700_투명점착_1500_WRF065_0_M7 | 28731_유광 S/R_1500_T02149_0_M7 | mixture_change+operation_type_change | 27210 | 27270 | 60 | 60 | 0 | 120
3 | 912 | 914 | 2 | pure_setup | 2 | 0 | 2 | 28731_유광 S/R_1500_T02149_0_M7 | 29059_유광 S/R_1500_W1809_0_M7 | mixture_change | 27360 | 27420 | 60 | 60 | 0 | 60
3 | 923 | 925 | 2 | pure_setup | 2 | 0 | 2 | 29059_유광 S/R_1500_W1809_0_M7 | 31023_ISR(하드코팅)_1500_W1818_0_M7 | mixture_change | 27690 | 27750 | 60 | 60 | 0 | 60
3 | 929 | 931 | 2 | pure_setup | 2 | 0 | 2 | 31023_ISR(하드코팅)_1500_W1818_0_M7 | 32316_ISR(하드코팅)_1500_T02150_0_M7 | mixture_change | 27870 | 27930 | 60 | 60 | 0 | 60
3 | 934 | 938 | 4 | setup_plus_idle | 2 | 2 | 2 | 32316_ISR(하드코팅)_1500_T02150_0_M7 | 31023_투명점착_1500_T01750_0_M7 | mixture_change+operation_type_change | 28020 | 28140 | 120 | 60 | 60 | 60
3 | 943 | 947 | 4 | pure_setup | 4 | 0 | 4 | 31023_투명점착_1500_T01750_0_M7 | 32316_투명점착_1500_WRF065_0_M7 | mixture_change | 28290 | 28410 | 120 | 120 | 0 | 120
3 | 950 | 954 | 4 | pure_setup | 4 | 0 | 4 | 32316_투명점착_1500_WRF065_0_M7 | 32221_투명점착_1500_T01750_0_M7 | mixture_change | 28500 | 28620 | 120 | 120 | 0 | 120
3 | 971 | 973 | 2 | pure_setup | 2 | 0 | 4 | 32221_투명점착_1500_T01750_0_M7 | 32730_MIBK SR_1500_T02149_0_M7 | mixture_change+operation_type_change | 29130 | 29190 | 60 | 60 | 0 | 120
3 | 975 | 979 | 4 | setup_plus_idle | 2 | 2 | 2 | 32730_MIBK SR_1500_T02149_0_M7 | 32730_투명점착_1500_T01750_0_M7 | mixture_change+operation_type_change | 29250 | 29370 | 120 | 60 | 60 | 60
4 | 632 | 639 | 7 | pure_idle | 0 | 7 | 0 | 32222_MIBK SR_1500_W1817_0_M6 | 30458_MIBK SR_1500_T02149_0_M7 | no_setup_machine | 18960 | 19170 | 210 | 0 | 210 | 0
4 | 641 | 646 | 5 | pure_idle | 0 | 5 | 0 | 30458_MIBK SR_1500_T02149_0_M7 | 31361_MIBK SR_1500_T01592_0_M7 | no_setup_machine | 19230 | 19380 | 150 | 0 | 150 | 0
4 | 648 | 879 | 231 | pure_idle | 0 | 231 | 0 | 31361_MIBK SR_1500_T01592_0_M7 | 32221_MIBK SR_1500_W1817_0_M7 | no_setup_machine | 19440 | 26370 | 6930 | 0 | 6930 | 0