## Sheet1
machine_index | gap_start | gap_end | gap_duration | gap_type | setup_time | idle_time | theoretical_setup_time | prev_task_id | next_task_id | setup_reason | gap_start_minutes | gap_end_minutes | gap_duration_minutes | setup_time_minutes | idle_time_minutes | theoretical_setup_time_minutes
0 | 53 | 55 | 2 | pure_setup | 2 | 0 | 4 | 32023_투명점착_1500_T0915_0_M5 | 31704_TOP COATING_1500_T01715_0_M5 | mixture_change+operation_type_change | 1590 | 1650 | 60 | 60 | 0 | 120
0 | 57 | 59 | 2 | pure_setup | 2 | 0 | 2 | 31704_TOP COATING_1500_T01715_0_M5 | 32023_TOP COATING_1500_T01713_0_M5 | mixture_change | 1710 | 1770 | 60 | 60 | 0 | 60
0 | 62 | 66 | 4 | setup_plus_idle | 2 | 2 | 2 | 32023_TOP COATING_1500_T01713_0_M5 | 32528_비산점착_1300_T01862_4_M5 | mixture_change+operation_type_change+width_long_to_short | 1860 | 1980 | 120 | 60 | 60 | 60
0 | 80 | 82 | 2 | pure_setup | 2 | 0 | 4 | 32528_비산점착_1300_T01862_4_M5 | 31772_ESR_1300_T01020_4_M5 | mixture_change+operation_type_change | 2400 | 2460 | 60 | 60 | 0 | 120
0 | 87 | 91 | 4 | setup_plus_idle | 2 | 2 | 2 | 31772_ESR_1300_T01020_4_M5 | 31772_비산점착_1300_T01226_4_M5 | mixture_change+operation_type_change | 2610 | 2730 | 120 | 60 | 60 | 60
0 | 95 | 99 | 4 | pure_setup | 4 | 0 | 4 | 31772_비산점착_1300_T01226_4_M5 | 29059_비산점착_1500_T01792_0_M6 | mixture_change+width_short_to_long | 2850 | 2970 | 120 | 120 | 0 | 120
0 | 119 | 123 | 4 | pure_setup | 4 | 0 | 4 | 29059_비산점착_1500_T01792_0_M6 | 32470_PPF점착_1500_T0915_0_M6 | mixture_change | 3570 | 3690 | 120 | 120 | 0 | 120
0 | 125 | 129 | 4 | pure_setup | 4 | 0 | 4 | 32470_PPF점착_1500_T0915_0_M6 | 32739_PPF점착_1500_T02098_0_M6 | mixture_change | 3750 | 3870 | 120 | 120 | 0 | 120
0 | 135 | 137 | 2 | pure_setup | 2 | 0 | 4 | 32739_PPF점착_1500_T02098_0_M6 | 32470_TOP COATING_1500_T01521_0_M6 | mixture_change+operation_type_change | 4050 | 4110 | 60 | 60 | 0 | 120
0 | 139 | 141 | 2 | pure_setup | 2 | 0 | 2 | 32470_TOP COATING_1500_T01521_0_M6 | 32739_TOP COATING_1500_T02244_0_M6 | mixture_change | 4170 | 4230 | 60 | 60 | 0 | 60
0 | 147 | 151 | 4 | setup_plus_idle | 2 | 2 | 2 | 32739_TOP COATING_1500_T02244_0_M6 | 25033_염료점착_1500_T02516_0_M6 | mixture_change+operation_type_change | 4410 | 4530 | 120 | 60 | 60 | 60
0 | 156 | 160 | 4 | pure_setup | 4 | 0 | 4 | 25033_염료점착_1500_T02516_0_M6 | 25278_비산점착_1500_T02560_0_M6 | mixture_change+operation_type_change | 4680 | 4800 | 120 | 120 | 0 | 120
0 | 186 | 188 | 2 | pure_setup | 2 | 0 | 4 | 25278_비산점착_1500_T02560_0_M6 | 31772_ESR_1300_T01020_4_M6 | mixture_change+operation_type_change+width_long_to_short | 5580 | 5640 | 60 | 60 | 0 | 120
0 | 311 | 313 | 2 | pure_setup | 2 | 0 | 2 | 32556_ESR_1300_T01020_4_M6 | 32556_ESR_1000_T01020_1_M6 | width_long_to_short | 9330 | 9390 | 60 | 60 | 0 | 60
0 | 331 | 335 | 4 | setup_plus_idle | 2 | 2 | 2 | 32556_ESR_1000_T01020_1_M6 | 31772_비산점착_1300_T01226_4_M6 | mixture_change+operation_type_change+width_short_to_long | 9930 | 10050 | 120 | 60 | 60 | 60
0 | 433 | 435 | 2 | pure_setup | 2 | 0 | 2 | 32556_비산점착_1300_T01226_4_M6 | 32556_비산점착_1000_T01226_1_M6 | width_long_to_short | 12990 | 13050 | 60 | 60 | 0 | 60
0 | 449 | 451 | 2 | pure_setup | 2 | 0 | 4 | 32556_비산점착_1000_T01226_1_M6 | 32174_TOP COATING_1500_T02116_0_M6 | mixture_change+operation_type_change+width_short_to_long | 13470 | 13530 | 60 | 60 | 0 | 120
0 | 452 | 456 | 4 | setup_plus_idle | 2 | 2 | 2 | 32174_TOP COATING_1500_T02116_0_M6 | 32174_PPF점착_1500_T01852_0_M6 | mixture_change+operation_type_change | 13560 | 13680 | 120 | 60 | 60 | 60
0 | 457 | 461 | 4 | pure_setup | 4 | 0 | 4 | 32174_PPF점착_1500_T01852_0_M6 | 32687_안료접착_1500_T02451_0_M6 | mixture_change+operation_type_change | 13710 | 13830 | 120 | 120 | 0 | 120
0 | 464 | 468 | 4 | pure_setup | 4 | 0 | 4 | 32687_안료접착_1500_T02451_0_M6 | 32693_안료접착_1500_T02428_0_M6 | mixture_change | 13920 | 14040 | 120 | 120 | 0 | 120
0 | 471 | 475 | 4 | pure_setup | 4 | 0 | 4 | 32693_안료접착_1500_T02428_0_M6 | 32199_안료접착_1500_T01445_0_M6 | mixture_change | 14130 | 14250 | 120 | 120 | 0 | 120
0 | 477 | 481 | 4 | pure_setup | 4 | 0 | 4 | 32199_안료접착_1500_T01445_0_M6 | 31016_안료접착_1500_T02520_0_M6 | mixture_change | 14310 | 14430 | 120 | 120 | 0 | 120
0 | 483 | 487 | 4 | pure_setup | 4 | 0 | 4 | 31016_안료접착_1500_T02520_0_M6 | 32023_투명점착_1500_T0915_0_M6 | mixture_change+operation_type_change | 14490 | 14610 | 120 | 120 | 0 | 120
0 | 498 | 502 | 4 | pure_setup | 4 | 0 | 4 | 32023_투명점착_1500_T0915_0_M6 | 32199_투명점착_1500_T01306_0_M6 | mixture_change | 14940 | 15060 | 120 | 120 | 0 | 120
0 | 504 | 506 | 2 | pure_setup | 2 | 0 | 4 | 32199_투명점착_1500_T01306_0_M6 | 32023_TOP COATING_1500_T01713_0_M6 | mixture_change+operation_type_change | 15120 | 15180 | 60 | 60 | 0 | 120
0 | 517 | 519 | 2 | pure_setup | 2 | 0 | 2 | 32023_TOP COATING_1500_T01713_0_M6 | 32199_TOP COATING_1500_T01576_0_M6 | mixture_change | 15510 | 15570 | 60 | 60 | 0 | 60
0 | 521 | 525 | 4 | setup_plus_idle | 2 | 2 | 2 | 32199_TOP COATING_1500_T01576_0_M6 | 32474_안료점착_1500_T01445_0_M6 | mixture_change+operation_type_change | 15630 | 15750 | 120 | 60 | 60 | 60
0 | 526 | 530 | 4 | pure_setup | 4 | 0 | 4 | 32474_안료점착_1500_T01445_0_M6 | 32474_PPF점착_1500_T01306_0_M6 | mixture_change+operation_type_change | 15780 | 15900 | 120 | 120 | 0 | 120
0 | 531 | 535 | 4 | pure_setup | 4 | 0 | 4 | 32474_PPF점착_1500_T01306_0_M6 | 32415_PPF점착_1500_T02116_0_M6 | mixture_change | 15930 | 16050 | 120 | 120 | 0 | 120
0 | 541 | 545 | 4 | pure_setup | 4 | 0 | 4 | 32415_PPF점착_1500_T02116_0_M6 | 32453_PPF점착_1500_T01543_0_M6 | mixture_change | 16230 | 16350 | 120 | 120 | 0 | 120
0 | 556 | 558 | 2 | pure_setup | 2 | 0 | 4 | 32453_PPF점착_1500_T01543_0_M6 | 32474_TOP COATING_1500_T02244_0_M6 | mixture_change+operation_type_change | 16680 | 16740 | 60 | 60 | 0 | 120
0 | 570 | 572 | 2 | pure_setup | 2 | 0 | 2 | 32453_TOP COATING_1500_T02244_0_M6 | 32415_TOP COATING_1500_T02116_0_M6 | mixture_change | 17100 | 17160 | 60 | 60 | 0 | 60
0 | 579 | 583 | 4 | setup_plus_idle | 2 | 2 | 2 | 32415_TOP COATING_1500_T02116_0_M6 | 32001_안료접착_1500_T02446_0_M6 | mixture_change+operation_type_change | 17370 | 17490 | 120 | 60 | 60 | 60
0 | 586 | 590 | 4 | pure_setup | 4 | 0 | 4 | 32001_안료접착_1500_T02446_0_M6 | 32472_BLACK EPU코팅_1500_14774_0_M6 | mixture_change+operation_type_change | 17580 | 17700 | 120 | 120 | 0 | 120
0 | 594 | 596 | 2 | pure_setup | 2 | 0 | 4 | 32472_BLACK EPU코팅_1500_14774_0_M6 | 32472_TOP COATING_1500_T01514_0_M6 | mixture_change+operation_type_change | 17820 | 17880 | 60 | 60 | 0 | 120
0 | 599 | 603 | 4 | setup_plus_idle | 2 | 2 | 2 | 32472_TOP COATING_1500_T01514_0_M6 | 30566_안료접착_1500_T02150_0_M6 | mixture_change+operation_type_change | 17970 | 18090 | 120 | 60 | 60 | 60
0 | 606 | 610 | 4 | pure_setup | 4 | 0 | 4 | 30566_안료접착_1500_T02150_0_M6 | 32318_안료접착_1500_T02532_0_M6 | mixture_change | 18180 | 18300 | 120 | 120 | 0 | 120
0 | 615 | 617 | 2 | pure_setup | 2 | 0 | 2 | 32318_안료접착_1500_T02532_0_M6 | 32318_안료접착_1000_T02532_1_M6 | width_long_to_short | 18450 | 18510 | 60 | 60 | 0 | 60
0 | 620 | 624 | 4 | pure_setup | 4 | 0 | 4 | 32318_안료접착_1000_T02532_1_M6 | 32304_안료접착_1500_T02521_1_M6 | mixture_change+width_short_to_long | 18600 | 18720 | 120 | 120 | 0 | 120
0 | 626 | 630 | 4 | pure_setup | 4 | 0 | 4 | 32304_안료접착_1500_T02521_1_M6 | 32306_안료접착_1500_T02534_0_M6 | mixture_change | 18780 | 18900 | 120 | 120 | 0 | 120
0 | 633 | 635 | 2 | pure_setup | 2 | 0 | 2 | 32306_안료접착_1500_T02534_0_M6 | 32306_안료접착_1000_T02534_1_M6 | width_long_to_short | 18990 | 19050 | 60 | 60 | 0 | 60
0 | 641 | 645 | 4 | pure_setup | 4 | 0 | 4 | 32306_안료접착_1000_T02534_1_M6 | 32309_안료접착_1500_T01747_0_M6 | mixture_change+width_short_to_long | 19230 | 19350 | 120 | 120 | 0 | 120
0 | 651 | 655 | 4 | pure_setup | 4 | 0 | 4 | 32309_안료접착_1500_T01747_1_M6 | 32310_안료접착_1500_T01748_0_M6 | mixture_change | 19530 | 19650 | 120 | 120 | 0 | 120
0 | 658 | 660 | 2 | pure_setup | 2 | 0 | 2 | 32310_안료접착_1500_T01748_0_M6 | 32310_안료접착_1000_T01748_1_M6 | width_long_to_short | 19740 | 19800 | 60 | 60 | 0 | 60
0 | 667 | 671 | 4 | pure_setup | 4 | 0 | 4 | 32310_안료접착_1000_T01748_1_M6 | 32312_안료접착_1500_T01688_0_M6 | mixture_change+width_short_to_long | 20010 | 20130 | 120 | 120 | 0 | 120
0 | 676 | 680 | 4 | pure_setup | 4 | 0 | 4 | 32312_안료접착_1500_T01688_1_M6 | 32303_안료접착_1000_T01684_1_M6 | mixture_change+width_long_to_short | 20280 | 20400 | 120 | 120 | 0 | 120
0 | 684 | 688 | 4 | pure_setup | 4 | 0 | 4 | 32303_안료접착_1000_T01684_1_M6 | 32198_PPF점착_1500_T0915_0_M6 | mixture_change+operation_type_change+width_short_to_long | 20520 | 20640 | 120 | 120 | 0 | 120
0 | 689 | 691 | 2 | pure_setup | 2 | 0 | 4 | 32198_PPF점착_1500_T0915_0_M6 | 32198_TOP COATING_1500_T01576_0_M6 | mixture_change+operation_type_change | 20670 | 20730 | 60 | 60 | 0 | 120
0 | 692 | 694 | 2 | pure_setup | 2 | 0 | 2 | 32198_TOP COATING_1500_T01576_0_M6 | 31772_ESR_1000_T01020_1_M6 | mixture_change+width_long_to_short | 20760 | 20820 | 60 | 60 | 0 | 60
0 | 702 | 706 | 4 | setup_plus_idle | 2 | 2 | 2 | 31772_ESR_1000_T01020_1_M6 | 31772_비산점착_1000_T01226_1_M6 | mixture_change+operation_type_change | 21060 | 21180 | 120 | 60 | 60 | 60
0 | 712 | 716 | 4 | pure_setup | 4 | 0 | 4 | 31772_비산점착_1000_T01226_1_M6 | 30863_비산점착_1500_W1558_0_M7 | mixture_change+width_short_to_long | 21360 | 21480 | 120 | 120 | 0 | 120
0 | 736 | 740 | 4 | pure_setup | 4 | 0 | 4 | 30863_비산접착(1차)_1500_W1558_0_M7 | 31023_안료접착_1500_T02404_0_M7 | mixture_change+operation_type_change | 22080 | 22200 | 120 | 120 | 0 | 120
0 | 746 | 750 | 4 | pure_setup | 4 | 0 | 4 | 31023_안료접착_1500_T02404_0_M7 | 31809_안료접착_1500_T01331_0_M7 | mixture_change | 22380 | 22500 | 120 | 120 | 0 | 120
0 | 752 | 756 | 4 | pure_setup | 4 | 0 | 4 | 31809_안료접착_1500_T01331_0_M7 | 32221_안료접착_1500_T02147_0_M7 | mixture_change | 22560 | 22680 | 120 | 120 | 0 | 120
0 | 779 | 783 | 4 | pure_setup | 4 | 0 | 4 | 32221_안료접착_1500_T02147_0_M7 | 32315_안료접착_1500_T02538_0_M7 | mixture_change | 23370 | 23490 | 120 | 120 | 0 | 120
0 | 788 | 792 | 4 | pure_setup | 4 | 0 | 4 | 32315_안료접착_1500_T02538_1_M7 | 31809_투명점착_1500_T01306_0_M7 | mixture_change+operation_type_change | 23640 | 23760 | 120 | 120 | 0 | 120
0 | 794 | 798 | 4 | pure_setup | 4 | 0 | 4 | 31809_투명점착_1500_T01306_0_M7 | 32023_투명점착_1500_T0915_0_M7 | mixture_change | 23820 | 23940 | 120 | 120 | 0 | 120
0 | 809 | 813 | 4 | pure_setup | 4 | 0 | 4 | 32023_투명점착_1500_T0915_0_M7 | 31809_TOP COATING_1500_T01715_0_M7 | mixture_change+operation_type_change | 24270 | 24390 | 120 | 120 | 0 | 120
0 | 815 | 817 | 2 | pure_setup | 2 | 0 | 2 | 31809_TOP COATING_1500_T01715_0_M7 | 32023_TOP COATING_1500_T01713_0_M7 | mixture_change | 24450 | 24510 | 60 | 60 | 0 | 60
0 | 828 | 830 | 2 | pure_setup | 2 | 0 | 2 | 32023_TOP COATING_1500_T01713_0_M7 | 31966_PPF점착_1500_T0915_0_M7 | mixture_change+operation_type_change | 24840 | 24900 | 60 | 60 | 0 | 60
0 | 896 | 900 | 4 | pure_setup | 4 | 0 | 4 | 31966_PPF점착_1500_T0915_0_M7 | 32431_PPF점착_1500_T01514_0_M7 | mixture_change | 26880 | 27000 | 120 | 120 | 0 | 120
0 | 903 | 907 | 4 | pure_setup | 4 | 0 | 4 | 32431_PPF점착_1500_T01514_0_M7 | 32431_TOP COATING_1500_T02116_0_M7 | mixture_change+operation_type_change | 27090 | 27210 | 120 | 120 | 0 | 120
0 | 911 | 913 | 2 | pure_setup | 2 | 0 | 2 | 32431_TOP COATING_1500_T02116_0_M7 | 32532_TOP COATING_1300_T02546_4_M7 | mixture_change+width_long_to_short | 27330 | 27390 | 60 | 60 | 0 | 60
0 | 953 | 969 | 16 | setup_plus_idle | 2 | 14 | 2 | 32532_TOP COATING_1300_T02546_4_M7 | 29059_비산점착_1500_T01792_0_M7 | mixture_change+operation_type_change+width_short_to_long | 28590 | 29070 | 480 | 60 | 420 | 60
0 | 985 | 987 | 2 | pure_setup | 2 | 0 | 4 | 29059_비산점착_1500_T01792_0_M7 | 31966_TOP COATING_1500_T01288_0_M7 | mixture_change+operation_type_change | 29550 | 29610 | 60 | 60 | 0 | 120
0 | 1070 | 1074 | 4 | setup_plus_idle | 2 | 2 | 2 | 31966_TOP COATING_1500_T01288_0_M7 | 32532_투명점착_1300_T01862_4_M7 | mixture_change+operation_type_change+width_long_to_short | 32100 | 32220 | 120 | 60 | 60 | 60
1 | 33 | 164 | 131 | pure_idle | 0 | 131 | 0 | 30151_인쇄_1500_배합X_2_M5 | 32244_인쇄_1500_배합X_1_M5 | no_setup_machine | 990 | 4920 | 3930 | 0 | 3930 | 0
1 | 169 | 183 | 14 | pure_idle | 0 | 14 | 0 | 32244_인쇄_1500_배합X_1_M5 | 32244_인쇄_1500_배합X_0_M5 | no_setup_machine | 5070 | 5490 | 420 | 0 | 420 | 0
1 | 193 | 232 | 39 | pure_idle | 0 | 39 | 0 | 31019_인쇄_1500_배합X_0_M6 | 32377_인쇄_1500_배합X_0_M6 | no_setup_machine | 5790 | 6960 | 1170 | 0 | 1170 | 0
1 | 254 | 293 | 39 | pure_idle | 0 | 39 | 0 | 32497_인쇄_1500_배합X_0_M6 | 32672_인쇄_1500_배합X_0_M6 | no_setup_machine | 7620 | 8790 | 1170 | 0 | 1170 | 0
1 | 300 | 303 | 3 | pure_idle | 0 | 3 | 0 | 32672_인쇄_1500_배합X_0_M6 | 32673_인쇄_1500_배합X_0_M6 | no_setup_machine | 9000 | 9090 | 90 | 0 | 90 | 0
1 | 334 | 337 | 3 | pure_idle | 0 | 3 | 0 | 31017_인쇄_1500_배합X_0_M6 | 31505_인쇄_1500_배합X_0_M6 | no_setup_machine | 10020 | 10110 | 90 | 0 | 90 | 0
1 | 341 | 379 | 38 | pure_idle | 0 | 38 | 0 | 31505_인쇄_1500_배합X_0_M6 | 31020_인쇄_1500_배합X_0_M6 | no_setup_machine | 10230 | 11370 | 1140 | 0 | 1140 | 0
1 | 406 | 408 | 2 | pure_idle | 0 | 2 | 0 | 31024_인쇄_1500_배합X_0_M6 | 31025_인쇄_1500_배합X_0_M6 | no_setup_machine | 12180 | 12240 | 60 | 0 | 60 | 0
1 | 425 | 442 | 17 | pure_idle | 0 | 17 | 0 | 32002_인쇄_1500_배합X_0_M6 | 31925_인쇄_1500_배합X_0_M6 | no_setup_machine | 12750 | 13260 | 510 | 0 | 510 | 0
1 | 446 | 450 | 4 | pure_idle | 0 | 4 | 0 | 31925_인쇄_1500_배합X_0_M6 | 30458_인쇄_1500_배합X_1_M6 | no_setup_machine | 13380 | 13500 | 120 | 0 | 120 | 0
1 | 463 | 478 | 15 | pure_idle | 0 | 15 | 0 | 31503_인쇄_1500_배합X_3_M6 | 31503_인쇄_1500_배합X_1_M6 | no_setup_machine | 13890 | 14340 | 450 | 0 | 450 | 0
1 | 489 | 495 | 6 | pure_idle | 0 | 6 | 0 | 32693_인쇄_1500_배합X_0_M6 | 31016_인쇄_1500_배합X_0_M6 | no_setup_machine | 14670 | 14850 | 180 | 0 | 180 | 0
1 | 499 | 504 | 5 | pure_idle | 0 | 5 | 0 | 31016_인쇄_1500_배합X_0_M6 | 30460_인쇄_1500_배합X_0_M6 | no_setup_machine | 14970 | 15120 | 150 | 0 | 150 | 0
1 | 511 | 515 | 4 | pure_idle | 0 | 4 | 0 | 30460_인쇄_1500_배합X_0_M6 | 30460_인쇄_1500_배합X_1_M6 | no_setup_machine | 15330 | 15450 | 120 | 0 | 120 | 0
1 | 532 | 554 | 22 | pure_idle | 0 | 22 | 0 | 30460_인쇄_1500_배합X_1_M6 | 32320_인쇄_1500_배합X_0_M6 | no_setup_machine | 15960 | 16620 | 660 | 0 | 660 | 0
1 | 610 | 613 | 3 | pure_idle | 0 | 3 | 0 | 32305_인쇄_1000_배합X_1_M6 | 30566_인쇄_1500_배합X_0_M6 | no_setup_machine | 18300 | 18390 | 90 | 0 | 90 | 0
1 | 617 | 690 | 73 | pure_idle | 0 | 73 | 0 | 30566_인쇄_1500_배합X_0_M6 | 32304_인쇄_1500_배합X_1_M6 | no_setup_machine | 18510 | 20700 | 2190 | 0 | 2190 | 0
1 | 694 | 695 | 1 | pure_idle | 0 | 1 | 0 | 32304_인쇄_1500_배합X_1_M6 | 32318_인쇄_1500_배합X_0_M6 | no_setup_machine | 20820 | 20850 | 30 | 0 | 30 | 0
1 | 795 | 801 | 6 | pure_idle | 0 | 6 | 0 | 31361_인쇄_1500_배합X_0_M7 | 32225_인쇄_1500_배합X_0_M6 | no_setup_machine | 23850 | 24030 | 180 | 0 | 180 | 0
1 | 849 | 850 | 1 | pure_idle | 0 | 1 | 0 | 32017_인쇄_1500_배합X_0_M7 | 31600_인쇄_1500_배합X_0_M7 | no_setup_machine | 25470 | 25500 | 30 | 0 | 30 | 0
1 | 858 | 882 | 24 | pure_idle | 0 | 24 | 0 | 31600_인쇄_1500_배합X_0_M7 | 31737_인쇄_1500_배합X_0_M7 | no_setup_machine | 25740 | 26460 | 720 | 0 | 720 | 0
1 | 886 | 887 | 1 | pure_idle | 0 | 1 | 0 | 31737_인쇄_1500_배합X_0_M7 | 31738_인쇄_1500_배합X_0_M7 | no_setup_machine | 26580 | 26610 | 30 | 0 | 30 | 0
1 | 937 | 940 | 3 | pure_idle | 0 | 3 | 0 | 32267_인쇄_1500_배합X_0_M7 | 32672_인쇄_1500_배합X_0_M7 | no_setup_machine | 28110 | 28200 | 90 | 0 | 90 | 0
1 | 958 | 985 | 27 | pure_idle | 0 | 27 | 0 | 32700_인쇄_1500_배합X_0_M7 | 31023_인쇄_1500_배합X_0_M7 | no_setup_machine | 28740 | 29550 | 810 | 0 | 810 | 0
1 | 998 | 1014 | 16 | pure_idle | 0 | 16 | 0 | 32315_인쇄_1500_배합X_1_M7 | 32221_인쇄_1500_배합X_0_M7 | no_setup_machine | 29940 | 30420 | 480 | 0 | 480 | 0
2 | 5 | 9 | 4 | pure_setup | 4 | 0 | 4 | 30151_안료접착_1500_T02159_2_M5 | 31539_염료점착_1500_T02299_1_M5 | mixture_change+operation_type_change | 150 | 270 | 120 | 120 | 0 | 120
2 | 57 | 61 | 4 | pure_setup | 4 | 0 | 4 | 31539_염료점착_1500_T02299_2_M5 | 31539_염료점착_1300_T02299_4_M5 | width_long_to_short | 1710 | 1830 | 120 | 120 | 0 | 120
2 | 76 | 80 | 4 | pure_setup | 4 | 0 | 4 | 31539_염료점착_1300_T02299_4_M5 | 31540_염료점착_1500_T02296_1_M5 | mixture_change+width_short_to_long | 2280 | 2400 | 120 | 120 | 0 | 120
2 | 110 | 114 | 4 | pure_setup | 4 | 0 | 4 | 31540_염료점착_1500_T02296_2_M5 | 31541_염료점착_1500_T02300_1_M5 | mixture_change | 3300 | 3420 | 120 | 120 | 0 | 120
2 | 126 | 130 | 4 | pure_setup | 4 | 0 | 4 | 31541_염료점착_1500_T02300_2_M5 | 31864_염료점착_1500_T02515_1_M5 | mixture_change | 3780 | 3900 | 120 | 120 | 0 | 120
2 | 145 | 149 | 4 | pure_setup | 4 | 0 | 4 | 31864_염료점착_1500_T02515_2_M5 | 32244_안료접착_1500_T02510_1_M5 | mixture_change+operation_type_change | 4350 | 4470 | 120 | 120 | 0 | 120
2 | 157 | 161 | 4 | pure_setup | 4 | 0 | 4 | 32244_안료접착_1500_T02510_0_M5 | 31019_안료접착_1500_T02038_0_M6 | mixture_change | 4710 | 4830 | 120 | 120 | 0 | 120
2 | 168 | 172 | 4 | pure_setup | 4 | 0 | 4 | 31019_안료접착_1500_T02038_0_M6 | 26193_투명점착_1500_T01786_0_M6 | mixture_change+operation_type_change | 5040 | 5160 | 120 | 120 | 0 | 120
2 | 178 | 182 | 4 | pure_setup | 4 | 0 | 4 | 26193_투명점착_1500_T01786_0_M6 | 28732_투명접착_1500_WRF065_0_M6 | mixture_change | 5340 | 5460 | 120 | 120 | 0 | 120
2 | 188 | 192 | 4 | pure_setup | 4 | 0 | 4 | 28732_투명점착_1500_WRF065_0_M6 | 32377_안료접착_1500_T02173_0_M6 | mixture_change+operation_type_change | 5640 | 5760 | 120 | 120 | 0 | 120
2 | 197 | 201 | 4 | pure_setup | 4 | 0 | 4 | 32377_안료접착_1500_T02173_0_M6 | 32378_안료접착_1500_T02174_0_M6 | mixture_change | 5910 | 6030 | 120 | 120 | 0 | 120
2 | 207 | 211 | 4 | pure_setup | 4 | 0 | 4 | 32378_안료접착_1500_T02174_0_M6 | 32495_안료접착_1500_T02083_0_M6 | mixture_change | 6210 | 6330 | 120 | 120 | 0 | 120
2 | 214 | 218 | 4 | pure_setup | 4 | 0 | 4 | 32495_안료접착_1500_T02083_0_M6 | 32497_안료접착_1500_W2028_0_M6 | mixture_change | 6420 | 6540 | 120 | 120 | 0 | 120
2 | 221 | 225 | 4 | pure_setup | 4 | 0 | 4 | 32497_안료접착_1500_W2028_0_M6 | 32672_안료접착_1500_T02383_0_M6 | mixture_change | 6630 | 6750 | 120 | 120 | 0 | 120
2 | 231 | 235 | 4 | pure_setup | 4 | 0 | 4 | 32672_안료접착_1500_T02383_0_M6 | 32673_안료접착_1500_T02384_0_M6 | mixture_change | 6930 | 7050 | 120 | 120 | 0 | 120
2 | 238 | 242 | 4 | pure_setup | 4 | 0 | 4 | 32673_안료접착_1500_T02384_0_M6 | 32674_안료접착_1500_T02385_0_M6 | mixture_change | 7140 | 7260 | 120 | 120 | 0 | 120
2 | 245 | 249 | 4 | pure_setup | 4 | 0 | 4 | 32674_안료접착_1500_T02385_0_M6 | 32688_안료접착_1500_T02417_0_M6 | mixture_change | 7350 | 7470 | 120 | 120 | 0 | 120
2 | 252 | 256 | 4 | pure_setup | 4 | 0 | 4 | 32688_안료접착_1500_T02417_0_M6 | 32689_안료접착_1500_T02418_0_M6 | mixture_change | 7560 | 7680 | 120 | 120 | 0 | 120
2 | 262 | 266 | 4 | pure_setup | 4 | 0 | 4 | 32689_안료접착_1500_T02418_0_M6 | 32694_안료접착_1500_T02422_0_M6 | mixture_change | 7860 | 7980 | 120 | 120 | 0 | 120
2 | 269 | 273 | 4 | pure_setup | 4 | 0 | 4 | 32694_안료접착_1500_T02422_0_M6 | 32695_안료접착_1500_T02416_0_M6 | mixture_change | 8070 | 8190 | 120 | 120 | 0 | 120
2 | 276 | 280 | 4 | pure_setup | 4 | 0 | 4 | 32695_안료접착_1500_T02416_0_M6 | 31017_안료접착_1500_T02031_0_M6 | mixture_change | 8280 | 8400 | 120 | 120 | 0 | 120
2 | 283 | 287 | 4 | pure_setup | 4 | 0 | 4 | 31017_안료접착_1500_T02031_0_M6 | 31505_안료접착_1500_T02093_0_M6 | mixture_change | 8490 | 8610 | 120 | 120 | 0 | 120
2 | 290 | 294 | 4 | pure_setup | 4 | 0 | 4 | 31505_안료접착_1500_T02093_0_M6 | 31020_안료접착_1500_T02228_0_M6 | mixture_change | 8700 | 8820 | 120 | 120 | 0 | 120
2 | 301 | 305 | 4 | pure_setup | 4 | 0 | 4 | 31020_안료접착_1500_T02228_0_M6 | 31021_안료접착_1500_T02229_0_M6 | mixture_change | 9030 | 9150 | 120 | 120 | 0 | 120
2 | 311 | 315 | 4 | pure_setup | 4 | 0 | 4 | 31021_안료접착_1500_T02229_0_M6 | 31024_안료접착_1500_T02118_0_M6 | mixture_change | 9330 | 9450 | 120 | 120 | 0 | 120
2 | 322 | 326 | 4 | pure_setup | 4 | 0 | 4 | 31024_안료접착_1500_T02118_0_M6 | 31025_안료접착_1500_T02119_0_M6 | mixture_change | 9660 | 9780 | 120 | 120 | 0 | 120
2 | 332 | 336 | 4 | pure_setup | 4 | 0 | 4 | 31025_안료접착_1500_T02119_0_M6 | 31026_안료접착_1500_T02372_0_M6 | mixture_change | 9960 | 10080 | 120 | 120 | 0 | 120
2 | 339 | 343 | 4 | pure_setup | 4 | 0 | 4 | 31026_안료접착_1500_T02372_0_M6 | 31925_안료접착_1500_T02405_0_M6 | mixture_change | 10170 | 10290 | 120 | 120 | 0 | 120
2 | 347 | 351 | 4 | pure_setup | 4 | 0 | 4 | 31925_안료접착_1500_T02405_0_M6 | 32002_안료접착_1500_T02441_0_M6 | mixture_change | 10410 | 10530 | 120 | 120 | 0 | 120
2 | 359 | 363 | 4 | pure_setup | 4 | 0 | 4 | 32002_안료접착_1500_T02441_0_M6 | 30458_안료접착_1500_T02158_1_M6 | mixture_change | 10770 | 10890 | 120 | 120 | 0 | 120
2 | 368 | 372 | 4 | pure_setup | 4 | 0 | 4 | 30458_안료접착_1500_T02158_3_M6 | 30460_안료접착_1500_T02020_0_M6 | mixture_change | 11040 | 11160 | 120 | 120 | 0 | 120
2 | 390 | 394 | 4 | pure_setup | 4 | 0 | 4 | 30460_안료접착_1500_T02020_1_M6 | 31382_안료접착_1500_T02028_0_M6 | mixture_change | 11700 | 11820 | 120 | 120 | 0 | 120
2 | 396 | 400 | 4 | pure_setup | 4 | 0 | 4 | 31382_안료접착_1500_T02028_1_M6 | 31503_안료접착_1500_T02027_0_M6 | mixture_change | 11880 | 12000 | 120 | 120 | 0 | 120
2 | 405 | 409 | 4 | pure_setup | 4 | 0 | 4 | 31503_안료접착_1500_T02027_3_M6 | 30148_IR접착_1500_T02542_0_M6 | mixture_change | 12150 | 12270 | 120 | 120 | 0 | 120
2 | 411 | 415 | 4 | pure_setup | 4 | 0 | 4 | 30148_IR접착_1500_T02542_0_M6 | 32320_안료접착_1500_T01696_0_M6 | mixture_change | 12330 | 12450 | 120 | 120 | 0 | 120
2 | 418 | 422 | 4 | pure_setup | 4 | 0 | 4 | 32320_안료접착_1500_T01696_0_M6 | 32717_안료접착_1500_T02537_0_M6 | mixture_change | 12540 | 12660 | 120 | 120 | 0 | 120
2 | 426 | 430 | 4 | pure_setup | 4 | 0 | 4 | 32717_안료접착_1500_T02537_0_M6 | 32718_안료접착_1500_T02536_0_M6 | mixture_change | 12780 | 12900 | 120 | 120 | 0 | 120
2 | 434 | 438 | 4 | pure_setup | 4 | 0 | 4 | 32718_안료접착_1500_T02536_0_M6 | 32719_안료접착_1500_T02535_0_M6 | mixture_change | 13020 | 13140 | 120 | 120 | 0 | 120
2 | 442 | 446 | 4 | pure_setup | 4 | 0 | 4 | 32719_안료접착_1500_T02535_0_M6 | 32305_안료접착_1500_T02522_0_M6 | mixture_change | 13260 | 13380 | 120 | 120 | 0 | 120
2 | 449 | 453 | 4 | pure_setup | 4 | 0 | 4 | 32305_안료접착_1500_T02522_0_M6 | 32305_안료접착_1000_T02522_1_M6 | width_long_to_short | 13470 | 13590 | 120 | 120 | 0 | 120
2 | 457 | 461 | 4 | pure_setup | 4 | 0 | 4 | 32305_안료접착_1000_T02522_1_M6 | 32307_안료접착_1500_T02524_0_M6 | mixture_change+width_short_to_long | 13710 | 13830 | 120 | 120 | 0 | 120
2 | 469 | 473 | 4 | pure_setup | 4 | 0 | 4 | 32307_안료접착_1500_T02524_1_M6 | 32311_안료접착_1500_T01687_0_M6 | mixture_change | 14070 | 14190 | 120 | 120 | 0 | 120
2 | 479 | 483 | 4 | pure_setup | 4 | 0 | 4 | 32311_안료접착_1500_T01687_1_M6 | 32313_안료접착_1500_T01689_0_M6 | mixture_change | 14370 | 14490 | 120 | 120 | 0 | 120
2 | 489 | 493 | 4 | pure_setup | 4 | 0 | 4 | 32313_안료접착_1500_T01689_1_M6 | 32314_안료접착_1500_T01690_0_M6 | mixture_change | 14670 | 14790 | 120 | 120 | 0 | 120
2 | 498 | 502 | 4 | pure_setup | 4 | 0 | 4 | 32314_안료접착_1500_T01690_1_M6 | 32319_안료접착_1500_T02531_0_M6 | mixture_change | 14940 | 15060 | 120 | 120 | 0 | 120
2 | 507 | 511 | 4 | pure_setup | 4 | 0 | 4 | 32319_안료접착_1500_T02531_1_M6 | 25280_비산점착_1500_W1558_0_M6 | mixture_change+operation_type_change | 15210 | 15330 | 120 | 120 | 0 | 120
2 | 519 | 523 | 4 | pure_setup | 4 | 0 | 4 | 25280_비산접착(1차)_1500_W1558_0_M6 | 25280_비산접착(2차)_1500_T0897_0_M6 | mixture_change | 15570 | 15690 | 120 | 120 | 0 | 120
2 | 527 | 531 | 4 | pure_setup | 4 | 0 | 4 | 25280_비산접착(2차)_1500_T0897_0_M6 | 32222_안료접착_1500_T02148_0_M6 | mixture_change+operation_type_change | 15810 | 15930 | 120 | 120 | 0 | 120
2 | 548 | 552 | 4 | pure_setup | 4 | 0 | 4 | 32222_안료접착_1500_T02148_0_M6 | 32225_안료접착_1500_T02142_0_M6 | mixture_change | 16440 | 16560 | 120 | 120 | 0 | 120
2 | 558 | 562 | 4 | pure_setup | 4 | 0 | 4 | 32225_안료접착_1500_T02142_0_M6 | 30458_안료접착_1500_T02158_0_M7 | mixture_change | 16740 | 16860 | 120 | 120 | 0 | 120
2 | 565 | 569 | 4 | pure_setup | 4 | 0 | 4 | 30458_안료접착_1500_T02158_0_M7 | 31361_안료접착_1500_T02403_0_M7 | mixture_change | 16950 | 17070 | 120 | 120 | 0 | 120
2 | 572 | 576 | 4 | pure_setup | 4 | 0 | 4 | 31361_안료접착_1500_T02403_0_M7 | 31600_안료접착_1500_T02295_0_M7 | mixture_change | 17160 | 17280 | 120 | 120 | 0 | 120
2 | 584 | 588 | 4 | pure_setup | 4 | 0 | 4 | 31600_안료접착_1500_T02295_0_M7 | 31652_안료접착_1500_T02303_0_M7 | mixture_change | 17520 | 17640 | 120 | 120 | 0 | 120
2 | 593 | 597 | 4 | pure_setup | 4 | 0 | 4 | 31652_안료접착_1500_T02303_0_M7 | 31737_안료접착_1500_T02016_0_M7 | mixture_change | 17790 | 17910 | 120 | 120 | 0 | 120
2 | 601 | 605 | 4 | pure_setup | 4 | 0 | 4 | 31737_안료접착_1500_T02016_0_M7 | 31738_안료접착_1500_T02363_0_M7 | mixture_change | 18030 | 18150 | 120 | 120 | 0 | 120
2 | 611 | 615 | 4 | pure_setup | 4 | 0 | 4 | 31738_안료접착_1500_T02363_0_M7 | 31739_안료접착_1500_T02364_0_M7 | mixture_change | 18330 | 18450 | 120 | 120 | 0 | 120
2 | 618 | 622 | 4 | pure_setup | 4 | 0 | 4 | 31739_안료접착_1500_T02364_0_M7 | 31798_안료접착_1500_T02014_0_M7 | mixture_change | 18540 | 18660 | 120 | 120 | 0 | 120
2 | 626 | 630 | 4 | pure_setup | 4 | 0 | 4 | 31798_안료접착_1500_T02014_0_M7 | 31800_안료접착_1500_T02126_0_M7 | mixture_change | 18780 | 18900 | 120 | 120 | 0 | 120
2 | 636 | 640 | 4 | pure_setup | 4 | 0 | 4 | 31800_안료접착_1500_T02126_0_M7 | 31802_안료접착_1500_T02015_0_M7 | mixture_change | 19080 | 19200 | 120 | 120 | 0 | 120
2 | 646 | 650 | 4 | pure_setup | 4 | 0 | 4 | 31802_안료접착_1500_T02015_0_M7 | 32016_안료접착_1500_T02318_0_M7 | mixture_change | 19380 | 19500 | 120 | 120 | 0 | 120
2 | 658 | 662 | 4 | pure_setup | 4 | 0 | 4 | 32016_안료접착_1500_T02318_0_M7 | 32017_안료접착_1500_T02319_0_M7 | mixture_change | 19740 | 19860 | 120 | 120 | 0 | 120
2 | 671 | 675 | 4 | pure_setup | 4 | 0 | 4 | 32017_안료접착_1500_T02319_0_M7 | 32260_안료접착_1500_T02186_0_M7 | mixture_change | 20130 | 20250 | 120 | 120 | 0 | 120
2 | 678 | 682 | 4 | pure_setup | 4 | 0 | 4 | 32260_안료접착_1500_T02186_0_M7 | 32261_안료접착_1500_T02185_0_M7 | mixture_change | 20340 | 20460 | 120 | 120 | 0 | 120
2 | 688 | 692 | 4 | pure_setup | 4 | 0 | 4 | 32261_안료접착_1500_T02185_0_M7 | 32262_안료접착_1500_T02131_0_M7 | mixture_change | 20640 | 20760 | 120 | 120 | 0 | 120
2 | 696 | 700 | 4 | pure_setup | 4 | 0 | 4 | 32262_안료접착_1500_T02131_0_M7 | 32264_안료접착_1500_T02219_0_M7 | mixture_change | 20880 | 21000 | 120 | 120 | 0 | 120
2 | 707 | 711 | 4 | pure_setup | 4 | 0 | 4 | 32264_안료접착_1500_T02219_0_M7 | 32266_안료접착_1500_T02500_0_M7 | mixture_change | 21210 | 21330 | 120 | 120 | 0 | 120
2 | 715 | 719 | 4 | pure_setup | 4 | 0 | 4 | 32266_안료접착_1500_T02500_0_M7 | 32267_안료접착_1500_T02555_0_M7 | mixture_change | 21450 | 21570 | 120 | 120 | 0 | 120
2 | 726 | 730 | 4 | pure_setup | 4 | 0 | 4 | 32267_안료접착_1500_T02555_0_M7 | 32672_안료접착_1500_T02383_0_M7 | mixture_change | 21780 | 21900 | 120 | 120 | 0 | 120
2 | 735 | 739 | 4 | pure_setup | 4 | 0 | 4 | 32672_안료접착_1500_T02383_0_M7 | 32674_안료접착_1500_T02385_0_M7 | mixture_change | 22050 | 22170 | 120 | 120 | 0 | 120
2 | 742 | 746 | 4 | pure_setup | 4 | 0 | 4 | 32674_안료접착_1500_T02385_0_M7 | 32692_안료접착_1500_T02426_0_M7 | mixture_change | 22260 | 22380 | 120 | 120 | 0 | 120
2 | 749 | 753 | 4 | pure_setup | 4 | 0 | 4 | 32692_안료접착_1500_T02426_0_M7 | 32700_안료접착_1500_T02391_0_M7 | mixture_change | 22470 | 22590 | 120 | 120 | 0 | 120
2 | 756 | 760 | 4 | pure_setup | 4 | 0 | 4 | 32700_안료접착_1500_T02391_0_M7 | 28731_투명접착_1500_WRF065_0_M7 | mixture_change+operation_type_change | 22680 | 22800 | 120 | 120 | 0 | 120
2 | 768 | 772 | 4 | pure_setup | 4 | 0 | 4 | 28731_투명점착_1500_WRF065_0_M7 | 32316_안료접착_1500_T02539_0_M7 | mixture_change+operation_type_change | 23040 | 23160 | 120 | 120 | 0 | 120
2 | 776 | 780 | 4 | pure_setup | 4 | 0 | 4 | 32316_안료접착_1500_T02539_0_M7 | 32730_안료접착_1500_T02493_0_M7 | mixture_change | 23280 | 23400 | 120 | 120 | 0 | 120
3 | 8 | 10 | 2 | pure_setup | 2 | 0 | 2 | 30151_MIBK SR_1500_T02149_2_M5 | 32528_유광 S/R_1300_T02149_4_M5 | width_long_to_short | 240 | 300 | 60 | 60 | 0 | 60
3 | 16 | 20 | 4 | setup_plus_idle | 2 | 2 | 2 | 32528_유광 S/R_1300_T02149_4_M5 | 30151_투명점착_1500_W2010_2_M5 | mixture_change+operation_type_change+width_short_to_long | 480 | 600 | 120 | 60 | 60 | 60
3 | 26 | 28 | 2 | pure_setup | 2 | 0 | 4 | 30151_투명점착_1500_W2010_2_M5 | 31539_유광 S/R_1500_T02149_1_M5 | mixture_change+operation_type_change | 780 | 840 | 60 | 60 | 0 | 120
3 | 37 | 39 | 2 | pure_setup | 2 | 0 | 2 | 31539_유광 S/R_1500_T02149_1_M5 | 29059_유광 S/R_1500_W1809_0_M6 | mixture_change | 1110 | 1170 | 60 | 60 | 0 | 60
3 | 51 | 57 | 6 | setup_plus_idle | 2 | 4 | 2 | 29059_유광 S/R_1500_W1809_0_M6 | 31539_유광 S/R_1500_T02149_2_M5 | mixture_change | 1530 | 1710 | 180 | 60 | 120 | 60
3 | 70 | 76 | 6 | setup_plus_idle | 2 | 4 | 2 | 31539_유광 S/R_1500_T02149_2_M5 | 31539_유광 S/R_1300_T02149_4_M5 | width_long_to_short | 2100 | 2280 | 180 | 60 | 120 | 60
3 | 83 | 85 | 2 | pure_setup | 2 | 0 | 2 | 31539_유광 S/R_1300_T02149_4_M5 | 25278_유광 S/R_1500_T02149_0_M6 | width_short_to_long | 2490 | 2550 | 60 | 60 | 0 | 60
3 | 106 | 110 | 4 | pure_idle | 0 | 4 | 0 | 31540_유광 S/R_1500_T02149_1_M5 | 31540_유광 S/R_1500_T02149_2_M5 | no_change_detected | 3180 | 3300 | 120 | 0 | 120 | 0
3 | 117 | 120 | 3 | pure_idle | 0 | 3 | 0 | 31540_유광 S/R_1500_T02149_2_M5 | 31541_유광 S/R_1500_T02149_1_M5 | no_change_detected | 3510 | 3600 | 90 | 0 | 90 | 0
3 | 124 | 126 | 2 | pure_idle | 0 | 2 | 0 | 31541_유광 S/R_1500_T02149_1_M5 | 31541_유광 S/R_1500_T02149_2_M5 | no_change_detected | 3720 | 3780 | 60 | 0 | 60 | 0
3 | 130 | 139 | 9 | setup_plus_idle | 2 | 7 | 2 | 31541_유광 S/R_1500_T02149_2_M5 | 31864_유광 S/R_1500_W1809_1_M5 | mixture_change | 3900 | 4170 | 270 | 60 | 210 | 60
3 | 149 | 154 | 5 | setup_plus_idle | 2 | 3 | 2 | 31864_유광 S/R_1500_W1809_2_M5 | 32244_ISR(하드코팅)_1500_W1818_1_M5 | mixture_change | 4470 | 4620 | 150 | 60 | 90 | 60
3 | 156 | 157 | 1 | pure_idle | 0 | 1 | 0 | 32244_ISR(하드코팅)_1500_W1818_1_M5 | 32244_ISR(하드코팅)_1500_W1818_0_M5 | no_change_detected | 4680 | 4710 | 30 | 0 | 30 | 0
3 | 159 | 161 | 2 | pure_setup | 2 | 0 | 2 | 32244_ISR(하드코팅)_1500_W1818_0_M5 | 32244_투명점착_1500_WRF065_1_M5 | mixture_change+operation_type_change | 4770 | 4830 | 60 | 60 | 0 | 60
3 | 164 | 168 | 4 | pure_setup | 4 | 0 | 4 | 32244_투명점착_1500_WRF065_1_M5 | 31019_ISR(하드코팅)_1500_W1818_0_M6 | mixture_change+operation_type_change | 4920 | 5040 | 120 | 120 | 0 | 120
3 | 177 | 181 | 4 | pure_setup | 4 | 0 | 4 | 31019_투명점착_1500_W1818_0_M6 | 32244_투명점착_1500_WRF065_0_M5 | mixture_change | 5310 | 5430 | 120 | 120 | 0 | 120
3 | 183 | 185 | 2 | pure_setup | 2 | 0 | 4 | 32244_투명점착_1500_WRF065_0_M5 | 25033_유광 S/R_1500_T02149_0_M6 | mixture_change+operation_type_change | 5490 | 5550 | 60 | 60 | 0 | 120
3 | 191 | 197 | 6 | setup_plus_idle | 2 | 4 | 2 | 28732_유광 S/R_1500_T02149_0_M6 | 32377_MIBK SR(항균)_1500_t01828_0_M6 | mixture_change | 5730 | 5910 | 180 | 60 | 120 | 60
3 | 200 | 207 | 7 | pure_idle | 0 | 7 | 0 | 32377_MIBK SR(항균)_1500_t01828_0_M6 | 32378_MIBK SR(항균)_1500_t01828_0_M6 | no_change_detected | 6000 | 6210 | 210 | 0 | 210 | 0
3 | 210 | 214 | 4 | setup_plus_idle | 2 | 2 | 2 | 32378_MIBK SR(항균)_1500_t01828_0_M6 | 32495_MIBK SR(항균)_1500_T01828_0_M6 | mixture_change | 6300 | 6420 | 120 | 60 | 60 | 60
3 | 216 | 221 | 5 | setup_plus_idle | 2 | 3 | 2 | 32495_MIBK SR(항균)_1500_T01828_0_M6 | 32497_MIBK SR(항균)_1500_t01828_0_M6 | mixture_change | 6480 | 6630 | 150 | 60 | 90 | 60
3 | 223 | 227 | 4 | setup_plus_idle | 2 | 2 | 2 | 32497_MIBK SR(항균)_1500_t01828_0_M6 | 32377_투명점착_1500_WRF065_0_M6 | mixture_change+operation_type_change | 6690 | 6810 | 120 | 60 | 60 | 60
3 | 243 | 245 | 2 | pure_setup | 2 | 0 | 4 | 32497_투명점착_1500_WRF065_0_M6 | 32672_ISR(항균)_1500_T01512_0_M6 | mixture_change+operation_type_change | 7290 | 7350 | 60 | 60 | 0 | 120
3 | 256 | 262 | 6 | pure_idle | 0 | 6 | 0 | 32674_ISR(항균)_1500_T01512_0_M6 | 32689_ISR(항균)_1500_T01512_0_M6 | no_change_detected | 7680 | 7860 | 180 | 0 | 180 | 0
3 | 267 | 269 | 2 | pure_idle | 0 | 2 | 0 | 32689_ISR(항균)_1500_T01512_0_M6 | 32694_ISR(항균)_1500_T01512_0_M6 | no_change_detected | 8010 | 8070 | 60 | 0 | 60 | 0
3 | 272 | 276 | 4 | pure_idle | 0 | 4 | 0 | 32694_ISR(항균)_1500_T01512_0_M6 | 32695_ISR(항균)_1500_T01512_0_M6 | no_change_detected | 8160 | 8280 | 120 | 0 | 120 | 0
3 | 279 | 281 | 2 | pure_setup | 2 | 0 | 2 | 32695_ISR(항균)_1500_T01512_0_M6 | 32688_ISR(항균)_1500_W2026_0_M6 | mixture_change | 8370 | 8430 | 60 | 60 | 0 | 60
3 | 284 | 288 | 4 | setup_plus_idle | 2 | 2 | 2 | 32688_ISR(항균)_1500_W2026_0_M6 | 32672_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 8520 | 8640 | 120 | 60 | 60 | 60
3 | 296 | 300 | 4 | pure_setup | 4 | 0 | 4 | 32674_투명점착_1500_T01750_0_M6 | 32673_투명점착_1500_WRF065_0_M6 | mixture_change | 8880 | 9000 | 120 | 120 | 0 | 120
3 | 317 | 321 | 4 | pure_setup | 4 | 0 | 4 | 32695_투명점착_1500_WRF065_0_M6 | 31017_MIBK SR_1500_T02149_0_M6 | mixture_change+operation_type_change | 9510 | 9630 | 120 | 120 | 0 | 120
3 | 325 | 327 | 2 | pure_setup | 2 | 0 | 2 | 31505_MIBK SR_1500_T02149_0_M6 | 31017_투명점착_1500_W1818_0_M6 | mixture_change+operation_type_change | 9750 | 9810 | 60 | 60 | 0 | 60
3 | 330 | 334 | 4 | pure_setup | 4 | 0 | 4 | 31017_투명점착_1500_W1818_0_M6 | 31505_투명점착_1500_WRF065_0_M6 | mixture_change | 9900 | 10020 | 120 | 120 | 0 | 120
3 | 337 | 341 | 4 | pure_setup | 4 | 0 | 4 | 31505_투명점착_1500_WRF065_0_M6 | 31020_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change+operation_type_change | 10110 | 10230 | 120 | 120 | 0 | 120
3 | 356 | 359 | 3 | pure_idle | 0 | 3 | 0 | 31026_ISR(하드코팅)_1500_T02150_0_M6 | 32002_ISR(하드코팅)_1500_T02150_0_M6 | no_change_detected | 10680 | 10770 | 90 | 0 | 90 | 0
3 | 363 | 365 | 2 | pure_setup | 2 | 0 | 2 | 32002_ISR(하드코팅)_1500_T02150_0_M6 | 31024_ISR(하드코팅)_1500_W1818_0_M6 | mixture_change | 10890 | 10950 | 60 | 60 | 0 | 60
3 | 370 | 372 | 2 | pure_setup | 2 | 0 | 2 | 31024_ISR(하드코팅)_1500_W1818_0_M6 | 31020_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 11100 | 11160 | 60 | 60 | 0 | 60
3 | 399 | 403 | 4 | pure_setup | 4 | 0 | 4 | 32002_투명점착_1500_T01750_0_M6 | 31025_투명점착_1500_W2026_0_M6 | mixture_change | 11970 | 12090 | 120 | 120 | 0 | 120
3 | 408 | 412 | 4 | pure_setup | 4 | 0 | 4 | 31025_투명점착_1500_W2026_0_M6 | 31925_MIBK SR_1500_T02149_0_M6 | mixture_change+operation_type_change | 12240 | 12360 | 120 | 120 | 0 | 120
3 | 433 | 435 | 2 | pure_setup | 2 | 0 | 2 | 31503_MIBK SR_1500_T02149_3_M6 | 31382_MIBK SR_1500_W1817_0_M6 | mixture_change | 12990 | 13050 | 60 | 60 | 0 | 60
3 | 437 | 439 | 2 | pure_setup | 2 | 0 | 2 | 31382_MIBK SR_1500_W1817_1_M6 | 31925_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 13110 | 13170 | 60 | 60 | 0 | 60
3 | 442 | 446 | 4 | pure_setup | 4 | 0 | 4 | 31925_투명점착_1500_T01750_0_M6 | 30458_투명점착_1500_W2010_1_M6 | mixture_change | 13260 | 13380 | 120 | 120 | 0 | 120
3 | 453 | 457 | 4 | pure_setup | 4 | 0 | 4 | 31382_투명점착_1500_W2010_1_M6 | 31503_투명점착_1500_WRF065_0_M6 | mixture_change | 13590 | 13710 | 120 | 120 | 0 | 120
3 | 460 | 464 | 4 | pure_setup | 4 | 0 | 4 | 31503_투명점착_1500_WRF065_3_M6 | 32687_ISR(항균)_1500_W2026_0_M6 | mixture_change+operation_type_change | 13800 | 13920 | 120 | 120 | 0 | 120
3 | 467 | 471 | 4 | pure_idle | 0 | 4 | 0 | 32687_ISR(항균)_1500_W2026_0_M6 | 32693_ISR(항균)_1500_W2026_0_M6 | no_change_detected | 14010 | 14130 | 120 | 0 | 120 | 0
3 | 474 | 476 | 2 | pure_setup | 2 | 0 | 2 | 32693_ISR(항균)_1500_W2026_0_M6 | 31503_투명점착_1500_WRF065_1_M6 | mixture_change+operation_type_change | 14220 | 14280 | 60 | 60 | 0 | 60
3 | 484 | 486 | 2 | pure_setup | 2 | 0 | 4 | 32693_투명점착_1500_WRF065_0_M6 | 31016_MIBK SR_1500_T02149_0_M6 | mixture_change+operation_type_change | 14520 | 14580 | 60 | 60 | 0 | 120
3 | 488 | 490 | 2 | pure_setup | 2 | 0 | 2 | 31016_MIBK SR_1500_T02149_0_M6 | 32320_ISR(하드코팅)_1500_W1818_0_M6 | mixture_change | 14640 | 14700 | 60 | 60 | 0 | 60
3 | 497 | 499 | 2 | pure_setup | 2 | 0 | 2 | 32311_ISR(하드코팅)_1500_W1818_0_M6 | 30460_투명점착_1500_WRF065_0_M6 | mixture_change+operation_type_change | 14910 | 14970 | 60 | 60 | 0 | 60
3 | 515 | 519 | 4 | pure_setup | 4 | 0 | 4 | 30460_투명점착_1500_WRF065_1_M6 | 30148_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change+operation_type_change | 15450 | 15570 | 120 | 120 | 0 | 120
3 | 520 | 522 | 2 | pure_setup | 2 | 0 | 2 | 30148_ISR(하드코팅)_1500_T02150_0_M6 | 30148_투명점착_1500_W1818_0_M6 | mixture_change+operation_type_change | 15600 | 15660 | 60 | 60 | 0 | 60
3 | 526 | 528 | 2 | pure_setup | 2 | 0 | 2 | 32311_ISR(하드코팅)_1500_W1818_1_M6 | 32305_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change | 15780 | 15840 | 60 | 60 | 0 | 60
3 | 545 | 547 | 2 | pure_setup | 2 | 0 | 2 | 32319_ISR(하드코팅)_1500_T02150_1_M6 | 32305_ISR(하드코팅)_1000_T02150_1_M6 | width_long_to_short | 16350 | 16410 | 60 | 60 | 0 | 60
3 | 549 | 551 | 2 | pure_setup | 2 | 0 | 2 | 32305_ISR(하드코팅)_1000_T02150_1_M6 | 32320_투명점착_1500_WRF065_0_M6 | mixture_change+operation_type_change+width_short_to_long | 16470 | 16530 | 60 | 60 | 0 | 60
3 | 578 | 582 | 4 | pure_setup | 4 | 0 | 4 | 32319_투명점착_1500_WRF065_1_M6 | 32717_MIBK SR_1500_T02149_0_M6 | mixture_change+operation_type_change | 17340 | 17460 | 120 | 120 | 0 | 120
3 | 584 | 586 | 2 | pure_setup | 2 | 0 | 2 | 32717_MIBK SR_1500_T02149_0_M6 | 32001_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change | 17520 | 17580 | 60 | 60 | 0 | 60
3 | 588 | 592 | 4 | setup_plus_idle | 2 | 2 | 2 | 32001_ISR(하드코팅)_1500_T02150_0_M6 | 32001_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 17640 | 17760 | 120 | 60 | 60 | 60
3 | 595 | 599 | 4 | pure_setup | 4 | 0 | 4 | 32001_투명점착_1500_T01750_0_M6 | 32305_투명점착_1000_WRF065_1_M6 | mixture_change+width_long_to_short | 17850 | 17970 | 120 | 120 | 0 | 120
3 | 602 | 606 | 4 | pure_setup | 4 | 0 | 4 | 32305_투명점착_1000_WRF065_1_M6 | 30566_ISR(하드코팅)_1500_T02150_0_M6 | mixture_change+operation_type_change+width_short_to_long | 18060 | 18180 | 120 | 120 | 0 | 120
3 | 608 | 610 | 2 | pure_setup | 2 | 0 | 2 | 30566_ISR(하드코팅)_1500_T02150_0_M6 | 30566_투명점착_1500_W1818_0_M6 | mixture_change+operation_type_change | 18240 | 18300 | 60 | 60 | 0 | 60
3 | 613 | 615 | 2 | pure_idle | 0 | 2 | 0 | 30566_투명점착_1500_W1818_0_M6 | 32318_ISR(하드코팅)_1500_W1818_0_M6 | operation_type_change | 18390 | 18450 | 60 | 0 | 60 | 0
3 | 619 | 621 | 2 | pure_setup | 2 | 0 | 2 | 32318_ISR(하드코팅)_1500_W1818_0_M6 | 32318_ISR(하드코팅)_1000_W1818_1_M6 | width_long_to_short | 18570 | 18630 | 60 | 60 | 0 | 60
3 | 623 | 626 | 3 | setup_plus_idle | 2 | 1 | 2 | 32318_ISR(하드코팅)_1000_W1818_1_M6 | 32304_ISR(하드코팅)_1500_T02150_1_M6 | mixture_change+width_short_to_long | 18690 | 18780 | 90 | 60 | 30 | 60
3 | 630 | 633 | 3 | pure_idle | 0 | 3 | 0 | 31737_ISR(하드코팅)_1500_T02150_0_M7 | 32306_ISR(하드코팅)_1500_T02150_0_M6 | no_change_detected | 18900 | 18990 | 90 | 0 | 90 | 0
3 | 635 | 637 | 2 | pure_setup | 2 | 0 | 2 | 32306_ISR(하드코팅)_1500_T02150_0_M6 | 32718_MIBK SR_1500_T02149_0_M6 | mixture_change | 19050 | 19110 | 60 | 60 | 0 | 60
3 | 639 | 641 | 2 | pure_setup | 2 | 0 | 2 | 32718_MIBK SR_1500_T02149_0_M6 | 32306_ISR(하드코팅)_1000_T02150_1_M6 | mixture_change+width_long_to_short | 19170 | 19230 | 60 | 60 | 0 | 60
3 | 645 | 648 | 3 | setup_plus_idle | 2 | 1 | 2 | 32306_ISR(하드코팅)_1000_T02150_1_M6 | 32309_ISR(하드코팅)_1500_T02150_0_M6 | width_short_to_long | 19350 | 19440 | 90 | 60 | 30 | 60
3 | 650 | 651 | 1 | pure_idle | 0 | 1 | 0 | 32309_ISR(하드코팅)_1500_T02150_0_M6 | 32309_ISR(하드코팅)_1500_T02150_1_M6 | no_change_detected | 19500 | 19530 | 30 | 0 | 30 | 0
3 | 657 | 658 | 1 | pure_idle | 0 | 1 | 0 | 31738_ISR(하드코팅)_1500_T02150_0_M7 | 32310_ISR(하드코팅)_1500_T02150_0_M6 | no_change_detected | 19710 | 19740 | 30 | 0 | 30 | 0
3 | 660 | 662 | 2 | pure_setup | 2 | 0 | 2 | 32310_ISR(하드코팅)_1500_T02150_0_M6 | 32719_MIBK SR_1500_T02149_0_M6 | mixture_change | 19800 | 19860 | 60 | 60 | 0 | 60
3 | 664 | 667 | 3 | setup_plus_idle | 2 | 1 | 2 | 32719_MIBK SR_1500_T02149_0_M6 | 32310_ISR(하드코팅)_1000_T02150_1_M6 | mixture_change+width_long_to_short | 19920 | 20010 | 90 | 60 | 30 | 60
3 | 672 | 674 | 2 | pure_setup | 2 | 0 | 2 | 32310_ISR(하드코팅)_1000_T02150_1_M6 | 32312_ISR(하드코팅)_1500_T02150_0_M6 | width_short_to_long | 20160 | 20220 | 60 | 60 | 0 | 60
3 | 677 | 679 | 2 | pure_setup | 2 | 0 | 2 | 32312_ISR(하드코팅)_1500_T02150_1_M6 | 32225_MIBK SR_1500_T02149_0_M6 | mixture_change | 20310 | 20370 | 60 | 60 | 0 | 60
3 | 682 | 684 | 2 | pure_setup | 2 | 0 | 2 | 32225_MIBK SR_1500_T02149_0_M6 | 32303_ISR(하드코팅)_1000_T02150_1_M6 | mixture_change+width_long_to_short | 20460 | 20520 | 60 | 60 | 0 | 60
3 | 686 | 688 | 2 | pure_setup | 2 | 0 | 2 | 32303_ISR(하드코팅)_1000_T02150_1_M6 | 32304_투명점착_1500_WRF065_1_M6 | mixture_change+operation_type_change+width_short_to_long | 20580 | 20640 | 60 | 60 | 0 | 60
3 | 710 | 712 | 2 | pure_setup | 2 | 0 | 2 | 32312_투명점착_1500_WRF065_1_M6 | 32303_투명점착_1000_WRF065_1_M6 | width_long_to_short | 21300 | 21360 | 60 | 60 | 0 | 60
3 | 728 | 730 | 2 | pure_setup | 2 | 0 | 2 | 32318_투명점착_1000_WRF065_1_M6 | 32717_투명점착_1500_WRF065_0_M6 | width_short_to_long | 21840 | 21900 | 60 | 60 | 0 | 60
3 | 739 | 743 | 4 | pure_setup | 4 | 0 | 4 | 32719_투명점착_1500_WRF065_0_M6 | 32222_투명점착_1500_T01750_0_M6 | mixture_change | 22170 | 22290 | 120 | 120 | 0 | 120
3 | 758 | 762 | 4 | pure_setup | 4 | 0 | 4 | 32222_투명점착_1500_T01750_0_M6 | 30458_투명점착_1500_W2010_0_M7 | mixture_change | 22740 | 22860 | 120 | 120 | 0 | 120
3 | 768 | 770 | 2 | pure_setup | 2 | 0 | 4 | 31361_투명점착_1500_W2010_0_M7 | 31652_MIBK SR_1500_T02149_0_M7 | mixture_change+operation_type_change | 23040 | 23100 | 60 | 60 | 0 | 120
3 | 788 | 790 | 2 | pure_setup | 2 | 0 | 2 | 32017_MIBK SR_1500_T02149_0_M7 | 31798_MIBK SR_1500_W1817_0_M7 | mixture_change | 23640 | 23700 | 60 | 60 | 0 | 60
3 | 792 | 796 | 4 | setup_plus_idle | 2 | 2 | 2 | 31798_MIBK SR_1500_W1817_0_M7 | 32225_투명점착_1500_T01750_0_M6 | mixture_change+operation_type_change | 23760 | 23880 | 120 | 60 | 60 | 60
3 | 801 | 805 | 4 | pure_setup | 4 | 0 | 4 | 32225_투명점착_1500_T01750_0_M6 | 31652_투명점착_1500_WRF065_0_M7 | mixture_change | 24030 | 24150 | 120 | 120 | 0 | 120
3 | 833 | 835 | 2 | pure_setup | 2 | 0 | 4 | 32017_투명점착_1500_WRF065_0_M7 | 31600_WSR 코팅_1500_W1912_0_M7 | mixture_change+operation_type_change | 24990 | 25050 | 60 | 60 | 0 | 120
3 | 840 | 844 | 4 | setup_plus_idle | 2 | 2 | 2 | 31600_WSR 코팅_1500_W1912_0_M7 | 31600_투명점착_1500_WRF065_0_M7 | mixture_change+operation_type_change | 25200 | 25320 | 120 | 60 | 60 | 60
3 | 850 | 852 | 2 | pure_setup | 2 | 0 | 4 | 31600_투명점착_1500_WRF065_0_M7 | 32262_ISR(하드코팅)_1500_T02150_0_M7 | mixture_change+operation_type_change | 25500 | 25560 | 60 | 60 | 0 | 120
3 | 859 | 861 | 2 | pure_setup | 2 | 0 | 2 | 32264_ISR(하드코팅)_1500_T02150_0_M7 | 31739_ISR(하드코팅)_1500_W1818_0_M7 | mixture_change | 25770 | 25830 | 60 | 60 | 0 | 60
3 | 877 | 879 | 2 | pure_setup | 2 | 0 | 2 | 32315_ISR(하드코팅)_1500_W1818_0_M7 | 31737_투명점착_1500_WRF065_0_M7 | mixture_change+operation_type_change | 26310 | 26370 | 60 | 60 | 0 | 60
3 | 917 | 919 | 2 | pure_setup | 2 | 0 | 4 | 32267_투명점착_1500_WRF065_0_M7 | 32672_ISR(항균)_1500_T01512_0_M7 | mixture_change+operation_type_change | 27510 | 27570 | 60 | 60 | 0 | 120
3 | 932 | 936 | 4 | setup_plus_idle | 2 | 2 | 2 | 32700_ISR(항균)_1500_T01512_0_M7 | 32672_투명점착_1500_T01750_0_M7 | mixture_change+operation_type_change | 27960 | 28080 | 120 | 60 | 60 | 60
3 | 943 | 947 | 4 | pure_setup | 4 | 0 | 4 | 32674_투명점착_1500_T01750_0_M7 | 32692_투명점착_1500_WRF065_0_M7 | mixture_change | 28290 | 28410 | 120 | 120 | 0 | 120
3 | 953 | 955 | 2 | pure_setup | 2 | 0 | 4 | 32700_투명점착_1500_WRF065_0_M7 | 28731_유광 S/R_1500_T02149_0_M7 | mixture_change+operation_type_change | 28590 | 28650 | 60 | 60 | 0 | 120
3 | 958 | 960 | 2 | pure_setup | 2 | 0 | 2 | 28731_유광 S/R_1500_T02149_0_M7 | 29059_유광 S/R_1500_W1809_0_M7 | mixture_change | 28740 | 28800 | 60 | 60 | 0 | 60
3 | 969 | 971 | 2 | pure_setup | 2 | 0 | 2 | 29059_유광 S/R_1500_W1809_0_M7 | 31023_ISR(하드코팅)_1500_W1818_0_M7 | mixture_change | 29070 | 29130 | 60 | 60 | 0 | 60
3 | 976 | 980 | 4 | setup_plus_idle | 2 | 2 | 2 | 32315_ISR(하드코팅)_1500_W1818_1_M7 | 31023_투명점착_1500_T01750_0_M7 | mixture_change+operation_type_change | 29280 | 29400 | 120 | 60 | 60 | 60
3 | 985 | 989 | 4 | pure_setup | 4 | 0 | 4 | 31023_투명점착_1500_T01750_0_M7 | 32315_투명점착_1500_WRF065_0_M7 | mixture_change | 29550 | 29670 | 120 | 120 | 0 | 120
3 | 993 | 997 | 4 | pure_setup | 4 | 0 | 4 | 32315_투명점착_1500_WRF065_1_M7 | 32221_투명점착_1500_T01750_0_M7 | mixture_change | 29790 | 29910 | 120 | 120 | 0 | 120
3 | 1014 | 1016 | 2 | pure_setup | 2 | 0 | 4 | 32221_투명점착_1500_T01750_0_M7 | 32316_ISR(하드코팅)_1500_T02150_0_M7 | mixture_change+operation_type_change | 30420 | 30480 | 60 | 60 | 0 | 120
3 | 1019 | 1023 | 4 | setup_plus_idle | 2 | 2 | 2 | 32316_ISR(하드코팅)_1500_T02150_0_M7 | 32316_투명점착_1500_WRF065_0_M7 | mixture_change+operation_type_change | 30570 | 30690 | 120 | 60 | 60 | 60
3 | 1026 | 1028 | 2 | pure_setup | 2 | 0 | 4 | 32316_투명점착_1500_WRF065_0_M7 | 32730_MIBK SR_1500_T02149_0_M7 | mixture_change+operation_type_change | 30780 | 30840 | 60 | 60 | 0 | 120
3 | 1030 | 1034 | 4 | setup_plus_idle | 2 | 2 | 2 | 32730_MIBK SR_1500_T02149_0_M7 | 32730_투명점착_1500_T01750_0_M7 | mixture_change+operation_type_change | 30900 | 31020 | 120 | 60 | 60 | 60
4 | 558 | 565 | 7 | pure_idle | 0 | 7 | 0 | 32222_MIBK SR_1500_W1817_0_M6 | 30458_MIBK SR_1500_T02149_0_M7 | no_setup_machine | 16740 | 16950 | 210 | 0 | 210 | 0
4 | 567 | 572 | 5 | pure_idle | 0 | 5 | 0 | 30458_MIBK SR_1500_T02149_0_M7 | 31361_MIBK SR_1500_T01592_0_M7 | no_setup_machine | 17010 | 17160 | 150 | 0 | 150 | 0
4 | 574 | 779 | 205 | pure_idle | 0 | 205 | 0 | 31361_MIBK SR_1500_T01592_0_M7 | 32221_MIBK SR_1500_W1817_0_M7 | no_setup_machine | 17220 | 23370 | 6150 | 0 | 6150 | 0